## Summary
Innomesh Portal v4 — Regression Test Plan
Environment: https://v4-portal.dev.innomate.innomesh.com.au ¦ Build: Innomesh v4.0.0 ¦ Author: Chakrala Sai Charan ¦ Created: 10/06/2026 (from live UI exploration)
Scope: every actionable item post-login — navigation, dashboards, Hotlist (alerts & incidents), Vitals, Insights, Assets, Information, Integrations, Rooms, Axis AI, Administration, RBAC, NFR, plus live defects & historical edge cases.
Module / Sheet | Total | P1 | Pass | Fail | Blocked | Not Tested | % Executed | % Pass (of executed)
Global & Navigation | 35 | 11 | 0 | 0 | 0 | 35 | 0% | 0%
Dashboard | 15 | 6 | 0 | 0 | 0 | 15 | 0% | 0%
Alerts (Hotlist) | 48 | 23 | 0 | 0 | 0 | 48 | 0% | 0%
Incidents (Hotlist) | 23 | 15 | 0 | 0 | 0 | 23 | 0% | 0%
Vitals | 21 | 11 | 0 | 0 | 0 | 21 | 0% | 0%
Insights | 17 | 6 | 0 | 0 | 0 | 17 | 0% | 0%
Assets | 23 | 13 | 0 | 0 | 0 | 23 | 0% | 0%
Information | 12 | 5 | 0 | 0 | 0 | 12 | 0% | 0%
Integrations | 14 | 6 | 0 | 0 | 0 | 14 | 0% | 0%
Rooms | 21 | 12 | 0 | 0 | 0 | 21 | 0% | 0%
Axis AI | 12 | 4 | 0 | 0 | 0 | 12 | 0% | 0%
Administration | 40 | 28 | 0 | 0 | 0 | 40 | 0% | 0%
RBAC & Permissions | 19 | 14 | 0 | 0 | 0 | 19 | 0% | 0%
RM-Portal Consistency | 23 | 11 | 0 | 0 | 0 | 23 | 0% | 0%
Non-Functional | 20 | 7 | 0 | 0 | 0 | 20 | 0% | 0%
Known Issues & Edge Cases | 17 | 6 | 0 | 0 | 0 | 17 | 0% | 0%
TOTAL | 360 | 178 | 0 | 0 | 0 | 360 | 0% | 0%
How to use
• Status column has a dropdown: Not Tested / Pass / Fail / Blocked / N/A — colour-coded automatically.
• Priority: P1 = must pass every release (smoke/blocker), P2 = standard regression, P3 = nice-to-verify.
• Type: Smoke (critical path), Regression (feature behaviour), Edge (boundary/unusual), Negative (error handling).
• Automation column marks the intended harness (Playwright / Manual / API). Filter by it when scoping an automation sprint.
• Each sheet has autofilter + frozen header; use the Summary table above for live execution progress.
• 'Known Issues & Edge Cases' tracks open dev defects found on 10/06/2026 and historical edge cases — retest these every release.

## Global & Navigation
Global & Navigation — Regression Tests
Authentication, navigation, top bar, user menu, global chrome
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
GLB-001 | Authentication | Google SSO sign-in with corporate account | 1. Open portal URL in incognito 2. Complete Google authentication with innomate.com.au account | User lands on Dashboard; user card (bottom-left) shows correct name and email | P1 | Smoke | Manual | Not Tested
GLB-002 | Authentication | Unauthenticated access redirects to login | 1. Clear cookies / open incognito 2. Navigate directly to /hotlist/alerts/active | User is redirected to the Google auth flow; after login user is returned to the requested page (or Dashboard) | P1 | Regression | Playwright | Not Tested
GLB-003 | Authentication | Sign Out from user menu | 1. Click user card bottom-left 2. Click Sign Out | Session is terminated; user is returned to login; back button does not restore an authenticated session | P1 | Regression | Playwright | Not Tested
GLB-004 | Authentication | Session expiry handling | 1. Leave the portal idle past token expiry (or invalidate token) 2. Interact with any page | User is prompted to re-authenticate gracefully; no infinite spinners or silent empty data | P2 | Edge | Manual | Not Tested
GLB-005 | Authentication | Terms of Service acceptance for first-time user | 1. Login with a brand-new user account | Terms & Privacy popup appears; no page is accessible until accepted; popup does not reappear on next login | P1 | Regression | Playwright | Not Tested
GLB-006 | Navigation | All sidebar sections render for full-permission user | 1. Login as admin user 2. Inspect sidebar | Sections: Dashboard; Monitoring (Hotlist, Vitals); Analytics (Insights); Management (Assets, Information, Integrations, Rooms); AI (Axis AI); System (Administration) | P1 | Smoke | Playwright | Not Tested
GLB-007 | Navigation | Hotlist expands to Alerts and Incidents | 1. Click Hotlist in sidebar | Sub-items Alerts and Incidents appear; clicking each loads the corresponding page and highlights active item | P1 | Smoke | Playwright | Not Tested
GLB-008 | Navigation | Vitals expands to all 9 dashboards | 1. Click Vitals in sidebar | Sub-items: Infrastructure, Rooms, Network, Pulse, Sight, VNOC, Pods-2, Pods-3, Pods (custom dashboards reflect tenant config) | P2 | Regression | Playwright | Not Tested
GLB-009 | Navigation | Insights expands to all sub-dashboards | 1. Click Insights in sidebar | Sub-items: Rooms, Usage, Alerts, Proactive Support, Sight, Ops, Consumption, ECU Custom Insight, INPOD (tenant-custom items included) | P2 | Regression | Playwright | Not Tested
GLB-010 | Navigation | Sidebar collapse/expand via hamburger | 1. Click hamburger icon top-left 2. Click again | Sidebar collapses to icons / hides and restores; main content reflows without overlap; state persists across page navigation | P3 | Regression | Playwright | Not Tested
GLB-011 | Navigation | Sidebar scrolls independently with all sections expanded | 1. Expand every collapsible section | Sidebar gains its own scrollbar; user card remains pinned at bottom; no items unreachable | P3 | Edge | Playwright | Not Tested
GLB-012 | Navigation | Browser back/forward navigation | 1. Visit Dashboard > Alerts > an alert detail 2. Press browser Back twice, Forward twice | Each step restores the correct page and state; no blank screens or stale data | P2 | Regression | Playwright | Not Tested
GLB-013 | Navigation | Deep-link/refresh on every route | 1. Copy URL of each module page 2. Open each in a new tab (fresh load) | Each route renders its own module after the splash loader. KNOWN ISSUE: /integrations/appspace and /integrations/microsoft-teams-room render the QSC Q-Sys module on direct load | P1 | Regression | Playwright | Not Tested
GLB-014 | Top Bar | Site selector multi-select filters all data | 1. Open All Sites dropdown 2. Untick all but one site (e.g. innomateSydney) 3. Visit Dashboard, Alerts, Rooms | Dropdown lists All + each site (Inno, innomateSydney, innomateUK, innomateUS). All KPIs/tables/charts re-query and show only the selected site's data; selection persists across pages | P1 | Regression | Playwright | Not Tested
GLB-015 | Top Bar | Site selector 'All' checkbox behaviour | 1. Untick 'All' 2. Tick individual sites; re-tick All | 'All' toggles every site; individual ticks update 'All' state consistently (indeterminate/checked) | P2 | Regression | Playwright | Not Tested
GLB-016 | Top Bar | User Group selector filters all data | 1. Open All User Groups dropdown 2. Select a specific group (e.g. Demo Group) 3. Visit Alerts / Assets / Rooms | Single-select with tick mark; all module data is scoped to that user group; selection persists across navigation | P1 | Regression | Playwright | Not Tested
GLB-017 | Top Bar | User Group + Site combined filtering | 1. Select one site and one user group 2. Check Hotlist counts vs unfiltered | Counts reflect the intersection of both filters; no module ignores either filter | P1 | Edge | Manual | Not Tested
GLB-018 | Top Bar | Last Updated timestamp refreshes | 1. Note 'Last Updated' value 2. Wait for/trigger a data refresh | Timestamp updates (dd/mm/yyyy hh:mm:ss format) and matches the most recent data fetch | P3 | Regression | Playwright | Not Tested
GLB-019 | Top Bar | Applications grid (waffle) links | 1. Click grid icon top-right 2. Click each app entry | Lists Innomesh Room Manager, Innomesh Portal, Innomesh Documentation; Room Manager and Documentation open the correct external apps; Portal routes to Dashboard | P2 | Regression | Playwright | Not Tested
GLB-020 | Top Bar | Dark mode toggle | 1. Click moon icon 2. Browse Dashboard, Alerts, a detail page, dialogs 3. Toggle back | Entire UI switches theme with readable contrast (tables, badges, charts, modals); preference persists after reload | P2 | Regression | Playwright | Not Tested
GLB-021 | Top Bar | Notifications bell popover | 1. Click bell icon | Popover shows PROGRESS (n) and ERRORS (n) tabs with operation list or 'No active operations'; CLOSE dismisses; counts update during long-running ops (e.g. export, import) | P2 | Regression | Playwright | Not Tested
GLB-022 | Top Bar | Announcements (megaphone) icon | 1. Click megaphone icon | Announcements/what's-new content displays; dismiss works; no console errors | P3 | Regression | Manual | Not Tested
GLB-023 | Top Bar | Help (?) icon | 1. Click help icon on various pages | Context help/documentation opens for the current module | P3 | Regression | Manual | Not Tested
GLB-024 | User Menu | User menu contents | 1. Click user card bottom-left | Shows display name + full email, Terms of Service, Privacy Policy, Sign Out entries; Terms/Privacy open the correct documents | P2 | Regression | Playwright | Not Tested
GLB-025 | Chat Support | Support chat bubble | 1. Click chat bubble bottom-right 2. Send a test message (dev only) | Messenger opens within the page; widget does not overlap critical UI controls at common resolutions | P3 | Regression | Manual | Not Tested
GLB-026 | Loading | App splash loader on cold start | 1. Hard-refresh any page | Branded 'innomesh portal / Loading...' splash with version shows, then resolves to the requested route; no flash of unauthenticated content | P3 | Regression | Playwright | Not Tested
GLB-027 | Footer | Version label | 1. Check footer on all pages | 'Innomesh v4.0.0' (current build version) is displayed consistently | P3 | Smoke | Playwright | Not Tested
GLB-028 | Authentication | Session timeout dialog (implicit grant, no silent refresh) | 1. Login; let Cognito access token expire (or fast-forward) 2. Wait for the 30-min expiry check or make a request | Auth uses Cognito implicit grant — there is NO refresh token. Expired token triggers session-timeout dialog, clears localStorage tokens, redirects to login. No silent re-auth | P1 | Regression | Playwright | Not Tested
GLB-029 | Authentication | /unauthorized and 404 pages | 1. Access a permission-blocked route 2. Navigate to a garbage URL | Unauthorized page renders for blocked access; NotFound (404) page for unknown routes; both offer a way back | P2 | Regression | Playwright | Not Tested
GLB-030 | Navigation | Deep-link query params parity with v3 | 1. v3 supported /Hotlist?room={room}&asset={asset}&tab={severityIndex} 2. Test v4 equivalents (alert detail param routes /hotlist/alerts/detail/{alertId}/{assetId}/{roomId}) | Bookmarked v3-style deep links have a v4 equivalent or documented migration; v4 param routes resolve with partial params (alertId only, +assetId, +roomId) | P2 | Edge | Playwright | Not Tested
GLB-031 | Top Bar | Help system contextual key per page | 1. Press ? (or help icon) on Vitals, Hotlist, Admin, Rooms, Insights, Axis AI, Information detail | Help content matches page context (help keys portal-vitals, portal-hotlist, portal-admin, portal-rooms, portal-insights, portal-axis-ai, portal-room-information-detail) | P3 | Regression | Playwright | Not Tested
GLB-032 | Top Bar | System notices display + hash-based dismissal | 1. Publish a system notice (backend /notices) 2. Dismiss with 'don't show again' 3. Reload; then publish a CHANGED notice text | Notice modal shows on login; dismissal persists in localStorage by content hash; changed notice re-appears (new hash) | P2 | Regression | Playwright | Not Tested
GLB-033 | Top Bar | Fullscreen mode per page | 1. On Vitals and Insights click fullscreen toggle; press Escape 2. Reload page | data-fullscreen hides header/footer; Escape exits; preference persists per page key in localStorage (fullscreen_vitals etc.) | P3 | Regression | Playwright | Not Tested
GLB-034 | Chat Support | ZenDesk chat gated by permission + config | 1. Login as user WITH ip-live-chat permission (tenant config enableZenDesk=true) 2. Login as user WITHOUT the permission | Chat widget loads only when enableZenDesk config AND LiveChatAccess permission are both present; no script injected otherwise | P2 | Regression | Manual | Not Tested
GLB-035 | Analytics | Google Analytics page-view tracking | 1. With googleAnalyticsId configured, navigate several routes 2. Inspect gtag page_view events | GA script loads once; page_view fired per route change with correct page_path; no GA when ID not configured | P3 | Regression | Manual | Not Tested

## Dashboard
Dashboard — Regression Tests
Landing dashboard widgets, KPIs and cross-links
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
DSH-001 | KPI Cards | Five KPI cards render with data | 1. Open Dashboard 2. Wait for load | Cards show Active Alerts, Critical, Rooms Online, Rooms Occupied, Active Incidents with numeric values and coloured top borders; no card remains a skeleton after load completes. KNOWN ISSUE: cards intermittently stuck as skeletons | P1 | Smoke | Playwright | Not Tested
DSH-002 | KPI Cards | KPI values match module pages | 1. Note Active Alerts and Active Incidents counts 2. Open Hotlist > Alerts (ACTIVE tab) and Incidents (ACTIVE tab) | Dashboard counts equal the tab counts on the respective pages (within refresh window) | P1 | Regression | Playwright | Not Tested
DSH-003 | Alerts by Severity | Donut chart renders and reconciles | 1. Inspect Alerts by Severity widget | Donut shows total active count centred; legend High/Medium/Low segments sum to total; Claimed + Unclaimed footer figures sum to total | P1 | Regression | Playwright | Not Tested
DSH-004 | Alerts by Severity | 'View Hotlist' link | 1. Click View Hotlist -> | Navigates to /hotlist/alerts/active with no filter loss | P2 | Regression | Playwright | Not Tested
DSH-005 | Room Status | Room Status donut renders | 1. Inspect Room Status widget | Donut renders; Occupied / Maintenance footer counts match Rooms module figures; 'View Rooms ->' navigates to Rooms | P2 | Regression | Playwright | Not Tested
DSH-006 | Active Incidents | Incident breakdown widget | 1. Inspect Active Incidents widget | OPEN INCIDENTS total displayed; New / In Progress / On Hold rows sum to the total; 'View Incidents ->' navigates to Incidents page | P1 | Regression | Playwright | Not Tested
DSH-007 | Alert Trend | 7-day alert trend chart | 1. Inspect Alert Trend widget 2. Toggle legend items (Critical/High/Low/Medium) | Chart plots last 7 days with date axis; legend toggles hide/show series; tooltip values on hover are plausible vs alert history | P2 | Regression | Playwright | Not Tested
DSH-008 | Alert Trend | 'View Insights' link | 1. Click View Insights -> | Navigates to Insights > Alerts dashboard | P3 | Regression | Playwright | Not Tested
DSH-009 | Top Alerting Rooms | Top alerting rooms bar chart | 1. Inspect Top Alerting Rooms widget | Up to 5 rooms with bar + count, sorted descending; counts match per-room alert totals in Hotlist; 'View Rooms ->' works | P2 | Regression | Playwright | Not Tested
DSH-010 | Recent Alerts | Recent Critical & High Alerts table | 1. Inspect bottom table | Columns Time, Room, Device, Category, Severity, Summary; only CRITICAL/HIGH severities listed, newest first; 'View All ->' opens Hotlist | P2 | Regression | Playwright | Not Tested
DSH-011 | Recent Alerts | Row navigates to alert detail | 1. Click a row in Recent Critical & High Alerts | Opens the alert detail page for that alert | P2 | Regression | Playwright | Not Tested
DSH-012 | Refresh | Dashboard 'Updated <time>' stamp | 1. Note Updated stamp top-right 2. Leave page open past refresh interval | Widgets re-fetch periodically; Updated stamp advances; no flicker/duplication of widgets | P3 | Regression | Manual | Not Tested
DSH-013 | Filters | Dashboard respects Site / User Group selectors | 1. Select a single site, then a single user group 2. Observe all widgets | Every KPI, chart and table re-queries with the filter; totals shrink accordingly; no widget shows unfiltered data | P1 | Regression | Playwright | Not Tested
DSH-014 | Empty State | Dashboard under a filter with zero data | 1. Select a site/user-group combination with no rooms | Widgets show zero/empty states gracefully (no NaN, no infinite spinners, no errors) | P2 | Edge | Playwright | Not Tested
DSH-015 | Permissions | Dashboard widgets for restricted user | 1. Login as user without Hotlist/Rooms permissions | Widgets tied to unauthorised modules are hidden or show a permission message; links to unauthorised modules are not offered | P1 | Regression | Manual | Not Tested

## Alerts (Hotlist)
Alerts (Hotlist) — Regression Tests
Hotlist > Alerts: tabs, table, bulk & row actions, saved views, alert detail
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
ALR-001 | Tabs | Active tab loads with count | 1. Open Hotlist > Alerts | ACTIVE tab selected by default with row count badge (e.g. ACTIVE : 3380); table populated; count equals 'N alerts' label on the right | P1 | Smoke | Playwright | Not Tested
ALR-002 | Tabs | Resolved / Suppressed / History tabs | 1. Click each tab | URL changes to /hotlist/alerts/{active¦resolved¦suppressed¦history}; per-tab counts appear after lazy load (spinner in tab while counting); table content matches tab | P1 | Regression | Playwright | Not Tested
ALR-003 | Tabs | History capped at 1000 | 1. Open HISTORY tab in a tenancy with >1000 historical alerts | Count shows 1000 (cap); pagination works through all pages; export warns/includes capped set consistently | P3 | Edge | Playwright | Not Tested
ALR-004 | Tabs | Suppressed alerts show suppression context | 1. Open SUPPRESSED tab | Rows show SUPPRESSED badge; Owner column shows the suppressing user as a link; suppression correlates to room/asset definition (In Maintenance, Is Portable etc.) | P2 | Regression | Manual | Not Tested
ALR-005 | Table | Default sort and column sorting | 1. Verify default sort (Severity desc) 2. Click each sortable header twice | Each column sorts asc/desc with indicator; severity sorts by rank (Critical>High>Medium>Low>Notice) not alphabetically | P2 | Regression | Playwright | Not Tested
ALR-006 | Table | Severity badges colour-coded | 1. Inspect Severity column | CRITICAL/HIGH red, MEDIUM orange, LOW yellow, NOTICE grey (per design); colours consistent in dark mode | P3 | Regression | Playwright | Not Tested
ALR-007 | Table | Unclaimed owner highlighted | 1. Inspect Owner column | 'Unclaimed' renders in red; claimed alerts show owner name | P3 | Regression | Playwright | Not Tested
ALR-008 | Table | Pagination controls | 1. Change Rows per page (15 default) 2. Use first/prev/next/last | Page size options apply; 'Showing X to Y of Z entries' accurate; navigation buttons disable at bounds | P2 | Regression | Playwright | Not Tested
ALR-009 | Search | Search filters across fields | 1. Type a room name, then an asset name, then a description fragment | Result set narrows live (debounced); count label updates; clearing search restores full set | P1 | Regression | Playwright | Not Tested
ALR-010 | Search | Search with no matches | 1. Search a nonsense string | Empty state message; 0 alerts; no error | P2 | Negative | Playwright | Not Tested
ALR-011 | Saved Views | Save View As / Recall View / Delete View | 1. Apply search + column changes 2. Save icon > Save View As, name it 3. Reset, then Recall View > select it 4. Save icon > Delete View | View saved and listed in Recall View dropdown; recalling restores filters/columns; delete removes it (red action with confirm) | P1 | Regression | Playwright | Not Tested
ALR-012 | Saved Views | Saved view name collision / special chars | 1. Save two views with the same name; use emoji/long names | Duplicate names rejected or disambiguated; long names truncated gracefully in dropdown | P3 | Edge | Manual | Not Tested
ALR-013 | Columns | Column picker toggles | 1. Open column-settings icon 2. Untick Room; tick Zone and Ticket ID | Table updates instantly; choices persist for the session (and within saved views); picker lists Created, Resolved, Severity, Room, Zone, Asset, Category, Owner, Notes, Ticket ID, Description, Status | P2 | Regression | Playwright | Not Tested
ALR-014 | Bulk Actions | Select-all reveals bulk action bar | 1. Tick header checkbox | Floating bar shows 'N alerts selected' with Claim / Assign / Resolve / Suppress / X(clear); N equals visible selection (current page) | P1 | Regression | Playwright | Not Tested
ALR-015 | Bulk Actions | Bulk Claim | 1. Select 2+ unclaimed alerts 2. Click Claim | Owner becomes current user on all selected; Dashboard Claimed/Unclaimed split updates; audit trail records claim events | P1 | Regression | Playwright | Not Tested
ALR-016 | Bulk Actions | Bulk Assign to another user | 1. Select alerts > Assign 2. Pick a user | Assignee dialog lists portal users; owner updates to chosen user; assignee can see alerts under their name | P1 | Regression | Playwright | Not Tested
ALR-017 | Bulk Actions | Bulk Resolve | 1. Select alerts > Resolve (confirm) | Alerts move to RESOLVED tab; active count decrements; resolve event in alert history with actor + timestamp | P1 | Regression | Playwright | Not Tested
ALR-018 | Bulk Actions | Bulk Suppress | 1. Select alerts > Suppress (with reason if prompted) | Alerts move to SUPPRESSED tab with owner recorded; suppressed alerts no longer raise notifications nor count as active | P1 | Regression | Playwright | Not Tested
ALR-019 | Row Actions | Row kebab 'Claim Alert' | 1. Click kebab on an unclaimed active alert 2. Click Claim Alert | Alert owner set to current user; kebab options change appropriately for claimed state | P1 | Regression | Playwright | Not Tested
ALR-020 | Row Actions | Kebab options on resolved/suppressed alerts | 1. Open kebab on rows in RESOLVED and SUPPRESSED tabs | Only valid lifecycle actions offered (e.g. no Resolve on resolved; Unsuppress available on suppressed if supported) | P2 | Regression | Manual | Not Tested
ALR-021 | Delete | Delete (trash) icon behaviour | 1. Select alerts 2. Click trash icon | Confirmation required; deletion is permission-gated; deleted alerts removed from list and recorded in audit logs | P2 | Regression | Manual | Not Tested
ALR-022 | Export | Download/export current view | 1. Apply a filter 2. Click download icon | Export (CSV) contains exactly the filtered rows/visible columns; filename meaningful; large exports tracked under bell PROGRESS | P2 | Regression | Playwright | Not Tested
ALR-023 | Full History | Full History button | 1. Click 'Full History' top-right | Global alert history view opens (all lifecycle events); events are chronologically consistent — no resolve-twice, no resurface-without-resolve | P2 | Regression | Manual | Not Tested
ALR-024 | Detail | Row click opens alert detail | 1. Click an alert row | Routes to /hotlist/alerts/detail/{alertId}/{assetId}/{roomId}; breadcrumb Hotlist > room > asset; red banner shows summary + created timestamp; X returns to list | P1 | Smoke | Playwright | Not Tested
ALR-025 | Detail | Information tab panels | 1. Open detail > Information | Alert Details (Severity badge, Category, Claimed By, Current Value, Threshold Value); Asset Details (ID, Name link, Category, Manufacturer, Model, IP link, Hostname); Room Details (Room link, Room ID, Site, Zone, Host, Host IP); Other Information (Notes, User Group, Summary, Ticket ID, TDX #, Reference, MAC, Peripherals, Room Fields). '-' shown for empty values | P1 | Regression | Playwright | Not Tested
ALR-026 | Detail | Current vs Threshold values live | 1. Open a threshold-based alert (e.g. lamp hours) 2. Re-check after the metric changes | Current Value reflects live data and updates; Threshold Value matches the policy that raised the alert | P2 | Regression | Manual | Not Tested
ALR-027 | Detail | Asset Name / IP / Room links | 1. Click Asset Name link 2. Back; click IP address 3. Back; click Room link | Asset link opens asset detail; IP link opens device web UI (new tab); Room link opens room view. KNOWN ISSUE: room link observed as no-op in dev | P2 | Regression | Playwright | Not Tested
ALR-028 | Detail | History tab event log | 1. Open detail > History | Table: Timestamp, Alert ID, Event, Severity, Category, Owner, Notes, Diagnosis; events populated and in valid lifecycle order; VNOC-acknowledged alerts show ACK with hover notes | P2 | Regression | Manual | Not Tested
ALR-029 | Detail | Notes tab — save alert note | 1. Open detail > Notes 2. Type an alert note 3. Save | Save disabled until text entered; note persists after reload; note appears in alert history and Notes column in list | P1 | Regression | Playwright | Not Tested
ALR-030 | Detail | Asset Notes panel | 1. On Notes tab inspect Asset Notes | Asset-level notes load (separate fetch); editable per permissions; persist against the asset across alerts | P2 | Regression | Playwright | Not Tested
ALR-031 | Lifecycle | Alert resolve via fixing root cause | 1. Take an endpoint offline to raise 'Endpoint Responding' alert 2. Restore the endpoint | Alert auto-resolves; appears in RESOLVED with resolution timestamp; ServiceNow auto-incident (if enabled) resolves ~15 min later | P1 | Regression | Manual | Not Tested
ALR-032 | Lifecycle | New alert appears without manual refresh | 1. Keep ACTIVE tab open 2. Trigger a new alert in the environment | New alert appears (poll/refresh interval) without full page reload; Last Updated advances | P2 | Regression | Manual | Not Tested
ALR-033 | Permissions | Hotlist hidden without permission | 1. Login as user without Hotlist access | Hotlist nav item not shown; direct URL access blocked/redirected with message | P1 | Regression | Manual | Not Tested
ALR-034 | Data Integrity | No cross-tenant data | 1. Compare alert rooms/assets against tenancy inventory | Every alert references a room/asset belonging to the current tenant; no foreign tenant names appear | P1 | Regression | Manual | Not Tested
ALR-035 | Purge | Purge alerts dialog (permanent delete) | 1. Open purge dialog (requires manage permission) 2. Pick date range From/To + severity checkboxes (Critical/High/Medium/Low/Info) 3. Confirm with warning | Only alerts matching range+severities are permanently purged (POST /alerts/purge); warning states irreversibility; audit logged | P1 | Regression | Manual | Not Tested
ALR-036 | Ticketing | Create ServiceNow ticket from alert | 1. On an alert (tenant with ticketing=true) open Create Ticket 2. Verify fields: Impact (1-3), Urgency (1-3); Short Description/Description pre-populated from alert 3. Submit | Ticket created in ServiceNow, INC link shown on alert; AssignedTo / BusinessService / ConfigurationItem dropdowns appear ONLY when feature flags enableAssignedTo/enableBusinessService/enableConfigurationItem are on | P1 | Regression | Manual | Not Tested
ALR-037 | Ticketing | Ticket lifecycle: update / resolve / disassociate / reopen | 1. On an alert with a linked ticket: update fields; resolve with resolution code + notes; disassociate; reopen | Each operation hits ServiceNow and updates the alert's ticket panel state; resolve requires resolution code; disassociate breaks the link without deleting the SN ticket | P1 | Regression | Manual | Not Tested
ALR-038 | Ticketing | TDX ticket creation (tenant-flagged) | 1. On a tenant with alertConfig.tdx=true open Create TDX ticket 2. Submit | TDX ticket created via the v1 backend path (/v1/tdx/ticket); TDX option hidden when flag is false | P2 | Regression | Manual | Not Tested
ALR-039 | Ticketing | Custom alert notification (service request) | 1. Tenant with custom_alert_notification=true: open the custom action (labelled per custom_alert_notification_label) 2. Submit | Custom notification fires (POST /alert/custom_notification); action only visible when flag enabled; label matches tenant config | P2 | Regression | Manual | Not Tested
ALR-040 | Lifecycle | ServiceNow ACK on alert (v3 parity) | 1. Acknowledge an alert via the VNOC/ServiceNow ack flow 2. Hover/inspect ack indicator | alert.ack=true shows ACK badge; ack_notes visible on hover; ACK is distinct from Claim. PARITY CHECK: verify v4 implements the v3 servicenow-ack-dialog | P2 | Regression | Manual | Not Tested
ALR-041 | Lifecycle | SLA exclusion flag (non_sla) | 1. Toggle SLA flag on an alert (POST /alert/{id}/sla?non_sla=true) 2. Check SLA metrics in Insights/Proactive Support | non_sla alerts excluded from SLA/MTTR calculations; flag visible on alert; toggle permission-gated | P2 | Regression | Manual | Not Tested
ALR-042 | Suppression | Ignore rules: room-level vs asset-level with expiry | 1. Suppress at ROOM level; verify all room's alerts suppressed 2. Suppress one ASSET; verify only that asset suppressed 3. Set ignore_until date; advance past it | Two-level model (/ignorelist/room vs /ignorelist/asset); ignore_until date-based rules auto-expire and alerting resumes; rules listed and deletable in suppressed view | P1 | Regression | Manual | Not Tested
ALR-043 | Permissions | Severity-level view permissions | 1. Create role with only ip-hotlist-alerts-medium + ip-hotlist-alerts-low (no critical/high/notice/suppressed) 2. Login and view alerts | Only Medium/Low alerts visible (severity-gated rows/tabs); Suppressed tab requires ip-hotlist-alerts-suppressed; counts reflect visible severities only | P1 | Regression | Manual | Not Tested
ALR-044 | Table | Availability indicator on alert rows | 1. Enable availability column 2. Compare a room with a meeting in progress vs free room | Indicator shows free/busy/upcoming state sourced from room availability data; correct colours; tooltip explains state | P3 | Regression | Playwright | Not Tested
ALR-045 | Table | Column width/visibility persistence | 1. Resize columns + hide some; reload page 2. Check localStorage alerts-column-widths | Widths and visibility persist per table across sessions (localStorage); reset works; CSV export honours configured CSVHeaders from uiSettings | P3 | Regression | Playwright | Not Tested
ALR-046 | Real-time | WebSocket live updates + 30s refresh | 1. Keep Active tab open; raise a new alert 2. Kill the WS connection (devtools) and observe | New alerts appear via WebSocket without reload; fallback polling every 30s (HOTLIST_REFRESH_INTERVAL); WS reconnects with backoff (v3: 3s->60s, max 20 attempts) — verify v4 reconnect strategy | P1 | Regression | Manual | Not Tested
ALR-047 | History | Global alert history page (event-level) | 1. Open /hotlist/alerts/history-all 2. Verify events for: claim/unclaim, assign, suppress, resolve, ticket created, notes updated, ack | Event-level audit across all rooms (not just current state); filterable incl. by user group (v3 had a defect here); chronological integrity | P1 | Regression | Playwright | Not Tested
ALR-048 | AI | Alert AI diagnosis (v3 parity gap) | 1. v3 offered session-based AI diagnosis on Pulse alerts (/alerts/{id}/ai/query, /ai/diagnosis) 2. Check v4 alert detail for equivalent | PARITY CHECK: confirm whether alert-level AI diagnosis exists in v4 (vs Axis AI page only); if dropped, document as accepted delta | P2 | Edge | Manual | Not Tested

## Incidents (Hotlist)
Incidents (Hotlist) — Regression Tests
Hotlist > Incidents: lifecycle, create wizard, ServiceNow sync, rules
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
INC-001 | Tabs | Tab counts and content | 1. Open Hotlist > Incidents 2. Click ACTIVE / RESOLVED / ON HOLD / HISTORY | Counts per tab (e.g. ACTIVE : 228); URL updates per tab; rows match the state shown | P1 | Smoke | Playwright | Not Tested
INC-002 | Trend | SHOW TREND collapsible | 1. Click SHOW TREND | Incident trend chart expands above the table; collapsible toggles; data consistent with incident history | P3 | Regression | Playwright | Not Tested
INC-003 | Table | Incident table columns | 1. Inspect table | Priority badge (CRITICAL/HIGH/MODERATE/LOW), State badge (NEW/IN PROGRESS/ON HOLD/RESOLVED), Description, Room, Site, Assigned To, Created, Last Updated, ID (INC# + external ServiceNow link icon), Comments count; all sortable | P1 | Regression | Playwright | Not Tested
INC-004 | Table | ServiceNow external link icon | 1. Click the external-link icon next to an INC number | Opens the matching incident in ServiceNow in a new tab | P2 | Regression | Manual | Not Tested
INC-005 | Create | Create Incident wizard — step 1 validation | 1. Click + Create 2. Leave Incident Name empty; try Next | Next disabled until required fields completed; Incident Name marked * ; Cancel/X closes without creating | P1 | Regression | Playwright | Not Tested
INC-006 | Create | Scope radio switches selector | 1. In wizard choose Scope = Room, then Site, then Zone | Following dropdown switches between Room/Site/Zone pickers and clears prior selection | P2 | Regression | Playwright | Not Tested
INC-007 | Create | Priority computed from Impact x Urgency | 1. Select Impact High + Urgency Medium (and other combos) | Priority badge recomputes per the ITIL-style matrix (e.g. High+Medium=MODERATE); badge colour matches priority | P1 | Regression | Playwright | Not Tested
INC-008 | Create | Auto-Resolve checkbox | 1. Tick 'Auto-resolve when all associated alerts are resolved' 2. Create incident with associated alerts; resolve all alerts | Incident automatically resolves once every associated alert is resolved | P1 | Regression | Manual | Not Tested
INC-009 | Create | Step 2 — Associated Alerts | 1. Complete step 1 > Next 2. Search/select alerts to associate 3. Create | Alert picker lists/filters active alerts; created incident shows associations under its Associated Alerts tab | P1 | Regression | Playwright | Not Tested
INC-010 | Create | Created incident appears in list + ServiceNow | 1. Create a test incident (dev) | Row appears in ACTIVE with NEW state; if ServiceNow integration enabled an INC number is allocated and synchronised | P1 | Regression | Manual | Not Tested
INC-011 | Detail | Incident detail layout | 1. Click an incident row | Route /hotlist/incidents/detail/{INC#}; priority badge + title banner; tabs Information ¦ Associated Alerts ¦ Comments; Incident Details card shows source badge (ServiceNow), Incident Time, ID link, Category, Assigned To, Assignment Group, State, Impact, Urgency, Priority, Description; Room Details panel loads. KNOWN ISSUE: Room Details may hang 'Loading room details...'; SN description may show raw JSONata template | P1 | Regression | Playwright | Not Tested
INC-012 | Detail | Edit Information | 1. Click Edit Information 2. Change Assigned To / State / Description; save | Editable fields update; Last Updated changes; edits sync to ServiceNow where applicable | P1 | Regression | Manual | Not Tested
INC-013 | Detail | Comments tab | 1. Open Comments tab 2. Add a comment | Comment saved with author + timestamp; Comments count in the list increments; visible to other users | P2 | Regression | Playwright | Not Tested
INC-014 | Detail | Associated Alerts tab | 1. Open Associated Alerts | Lists linked alerts with severity/status; clicking navigates to the alert detail; resolving alerts updates the list | P2 | Regression | Playwright | Not Tested
INC-015 | Sync | ServiceNow synchronisation footer | 1. Check footer 'Last synchronised with ServiceNow' 2. Click refresh icon | Timestamp updates after manual refresh; remote changes in ServiceNow (state/assignee) appear after sync | P1 | Regression | Manual | Not Tested
INC-016 | Search/Views | Search, saved views, export | 1. Search incidents; save a view; export | Same view machinery as Alerts: search narrows, Recall/Save/Delete View work, export matches filtered set | P2 | Regression | Playwright | Not Tested
INC-017 | Auto-creation | ServiceNow Auto Incident Creation setting honoured | 1. Enable setting in Admin > Settings 2. Raise an alert and leave unresolved 15+ min | ServiceNow incident auto-created ~15 min after alert creation; auto-resolves ~15 min after alert resolution | P1 | Regression | Manual | Not Tested
INC-018 | Rules | Incident rules generate incidents | 1. Configure an enabled rule in Admin > Incidents (e.g. Severity High+, Qty 20+, Scope Global) 2. Breach the threshold | Incident is raised matching rule's Impact/Urgency; scope honoured (Room/Zone/Global aggregation) | P1 | Regression | Manual | Not Tested
INC-019 | Permissions | Incidents hidden without permission | 1. Login as user without incident permissions | Incidents nav item hidden; create/edit actions absent for read-only users | P1 | Regression | Manual | Not Tested
INC-020 | Sync | itsm_propagation flag on create/update | 1. Create/update an incident with itsm_propagation=true, then another with false | true: change syncs to ServiceNow/TDX; false: local-only change (no upstream write); verify header/param behaviour via BFF (POST /incident?itsm_propagation=...) | P1 | Regression | Manual | Not Tested
INC-021 | Resolve | Resolution codes on resolve | 1. Resolve an incident; inspect resolution code dropdown | Codes come from /incidents/resolution_codes; resolve requires a code; resolved incident moves to RESOLVED with code recorded | P1 | Regression | Manual | Not Tested
INC-022 | Lookups | State/impact/urgency option lists | 1. Compare Create/Edit dialog dropdowns to API responses (/incidents/states, /impact, /urgency, /categories) | Options match the backend lookups exactly (no hardcoded drift); ITSM integration type endpoint controls ServiceNow vs TDX behaviour | P2 | Regression | API | Not Tested
INC-023 | Comments | Comment add/edit/delete CRUD | 1. Add a comment; edit it; delete it (per RFC I5) | Full CRUD works with author+timestamp; count badge updates; sync to ITSM if applicable | P2 | Regression | Playwright | Not Tested

## Vitals
Vitals — Regression Tests
Vitals dashboards: Infrastructure, Rooms, Network, Pulse, Sight, custom
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
VIT-001 | Common | Time range selector on every Vitals view | 1. Open each Vitals view 2. Change 'Past 24 hours' to other ranges | All charts re-query for the selected window; axis labels update; selection persists while navigating between views | P1 | Regression | Playwright | Not Tested
VIT-002 | Common | Refresh button | 1. Click Refresh on any Vitals view | All visualisations refetch; spinners resolve; Last Updated advances | P2 | Regression | Playwright | Not Tested
VIT-003 | Common | Fullscreen expand | 1. Click expand icon | Dashboard enters fullscreen/kiosk mode; exit restores normal layout | P3 | Regression | Playwright | Not Tested
VIT-004 | Infrastructure | View loads without errors in time | 1. Open Vitals > Infrastructure | Loads < 10s; no auth/index errors; KPIs Avg CPU, Avg Memory, Avg Storage, Hosts Online (n/m) populated | P1 | Smoke | Playwright | Not Tested
VIT-005 | Infrastructure | All visualisations render with data | 1. Scroll through view | All Time CPU / Memory / Storage charts (per-host legend), Innomesh Healthcheck Response Time (all zones: Cluster A/B/C, Staging, Parking Lot), Host Response Time all render with plotted data | P1 | Regression | Playwright | Not Tested
VIT-006 | Infrastructure | Real Time Host Vitals table sanity | 1. Inspect host table | Each tenant host listed: CPU%, Memory%, Storage%, Uptime(days), Active badge, Zone; values 0-100%, uptime plausible; row count matches host count (no cross-tenant hosts) | P1 | Regression | Manual | Not Tested
VIT-007 | Infrastructure | VC-4 Service Vitals | 1. Inspect VC-4 table | Hosts running VC-4 listed with Uptime, Status RUNNING/STOPPED badge, Zone; status matches actual service state | P2 | Regression | Manual | Not Tested
VIT-008 | Vitals Rooms | Rooms vitals view loads | 1. Open Vitals > Rooms | KPIs Rooms Powered On / Rooms Occupied; charts Room Powered On %, Room Occupancy %, Rooms Powered On and Occupied by Zone; Room Vitals table lists every tenancy room with maintenance badge | P1 | Regression | Playwright | Not Tested
VIT-009 | Vitals Rooms | Counts correlate with tenancy | 1. Compare Rooms Powered On/Occupied numbers with environment (start a room via XPanel in DEV only) | Counts change when rooms power on/become occupied; never exceed total rooms in tenancy | P1 | Regression | Manual | Not Tested
VIT-010 | Vitals Rooms | Empty data handling | 1. View with a site filter having no active rooms | Charts show 'No data available' placeholders; KPIs show dash/zero; no errors | P2 | Edge | Playwright | Not Tested
VIT-011 | Network | Network view structure | 1. Open Vitals > Network | KPIs Total HTTP / DNS / TLS / Error Rate; charts Transaction Types, HTTP Transactions, DNS Transactions, TLS Sessions, Errors vs Successful, Errors Count Over Time, Latency Histogram, Response Times Distribution all render (or coherent empty states) | P2 | Regression | Playwright | Not Tested
VIT-012 | Pulse | Pulse view structure | 1. Open Vitals > Pulse | Monitors Status, Pings Over Time, Monitors List, Median Device Response Time (+ per Zone) render; monitor list matches configured Pulse monitors; response times plausible | P2 | Regression | Playwright | Not Tested
VIT-013 | Sight | Sight vitals view | 1. Open Vitals > Sight | CPU/Queries/Memory Over Time, Sight Worker Uptime, Asset Types with Most Errors, Median Sight Response Time, Response Time per Device render with data when Sight workers active | P2 | Regression | Playwright | Not Tested
VIT-014 | Custom | VNOC / Pods custom dashboards | 1. Open VNOC, Pods, Pods-2, Pods-3 | Tenant-specific visualisation sets render when configured; otherwise clean empty state 'You do not have any visualisations for <name>' — no crash | P2 | Regression | Playwright | Not Tested
VIT-015 | Data Integrity | No tenant cross-contamination | 1. Review host names, zones, room names across Vitals views | Only current tenant's infrastructure appears | P1 | Regression | Manual | Not Tested
VIT-016 | Permissions | Vitals hidden without permission | 1. Login as user without Vitals dashboard access | Vitals section absent from sidebar; direct URLs denied | P1 | Regression | Manual | Not Tested
VIT-017 | Compliance | Compliance tab renders (permission-gated) | 1. Grant ip-vitals-compliance; open Vitals > Compliance | Compliance bar/pie panels + violation tables (rooms/policies) render; tab hidden without permission. NOTE: tab not visible in dev nav — verify tenant tabLabels config includes it | P1 | Regression | Playwright | Not Tested
VIT-018 | Data Accuracy | Field-level accuracy vs raw Elasticsearch (Kibana->ECharts rewrite) | 1. For each Vitals chart, run the equivalent raw ES query (via /insights/search) 2. Compare rendered values field-by-field with v3.6 Kibana dashboards | ARCHITECTURAL CHANGE: v4 reimplemented all Vitals from Kibana iframes to native ECharts + direct ES. Aggregations, time bucketing, timezone boundaries, partial ranges and empty buckets must match v3.6 output exactly — visual similarity is NOT sufficient | P1 | Regression | Manual | Not Tested
VIT-019 | Data Accuracy | Time bucketing edge cases | 1. Test each chart with: single-day range, range crossing midnight (AEST/AEDT), 30-minute range, DST transition dates | Buckets align with v3.6 behaviour; no off-by-one-bucket or timezone shift; x-axis labels correct local time | P1 | Edge | Manual | Not Tested
VIT-020 | Controls | Exact date-range option set | 1. Open range dropdown on each tab | Options are Past 30 minutes / 4 hours / 24 hours / 3 days / 7 days (now-30m..now-7d), default 24h; selection re-queries all panels | P2 | Regression | Playwright | Not Tested
VIT-021 | Custom | Custom dashboards from tenant config | 1. Configure a custom Vitals dashboard (useCustomDashboards('Vitals')) 2. Verify tab appears with custom ID route /vitals/{customId} | Custom tabs render from uiSettings tabLabels with .show flag + ip-vitals-custom permission; removing config removes tab | P2 | Regression | Manual | Not Tested

## Insights
Insights — Regression Tests
Analytics dashboards incl. Consumption (billing) and custom insights
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
INS-001 | Common | Time range + refresh on all Insights views | 1. Open each Insights view 2. Change 'Past 3 days' range; click Refresh | Charts re-query; selection applies per view; no errors | P1 | Regression | Playwright | Not Tested
INS-002 | Rooms | Insights Rooms visualisations | 1. Open Insights > Rooms | Room Types, Room Usage, Rooms With Most Interactions, Room Powered On Over Time, Room Age, Total Rooms Over Time render with data or clean empty state | P2 | Regression | Playwright | Not Tested
INS-003 | Usage | Insights Usage visualisations | 1. Open Insights > Usage | Source Usage %, Display Usage, Source Usage, Most Used Devices, Source Usage Over Time, Most Common User Interactions render; 'No data available' when no usage telemetry | P2 | Regression | Playwright | Not Tested
INS-004 | Alerts | Insights Alerts dashboard | 1. Open Insights > Alerts | NEW ALERTS KPI; charts Alerts By Severity/Zone/Category, Active Alerts Over Time, Alerts Created Over Time, Alerts By Room, Alerts By Device Type; Alerts History table (Created, Room, Zone, Device, Category, Severity, Resolved) paginates 15/page up to 200 | P1 | Regression | Playwright | Not Tested
INS-005 | Alerts | KPI consistency with Hotlist | 1. Compare NEW ALERTS for the selected period vs Hotlist history | Counts consistent for equivalent period/filters; severity split matches | P2 | Regression | Manual | Not Tested
INS-006 | Alerts | History rows show full context | 1. Inspect Alerts History rows | Room/Zone/Device/Severity populated (not all '-'); Resolved Yes/No accurate | P2 | Regression | Manual | Not Tested
INS-007 | Proactive Support | MTTR metrics | 1. Open Insights > Proactive Support | Avg Alert Resolution Time (Hours), Avg Alert Response Time (Minutes), Alerts Report Per Person render; person-level report reflects claim/resolve actors | P2 | Regression | Manual | Not Tested
INS-008 | Sight | Sight insights | 1. Open Insights > Sight | Qty of Sight Enriched Assets KPI (matches enriched asset count), Sight Queries Over Time chart | P3 | Regression | Playwright | Not Tested
INS-009 | Ops | Ops insights + trigger history | 1. Open Insights > Ops | Ops Actions Triggered Over Time, Most Triggered Ops Actions, Rooms with Most Ops Actions, Top 10 Ops Users; Ops Trigger History table (Action, Room, User, Timestamp) pages 10/50; automation-triggered actions show user 'Automation' | P2 | Regression | Playwright | Not Tested
INS-010 | Consumption | Consumption/licensing dashboard | 1. Open Insights > Consumption | KPIs Active Rooms, Rooms Added/Removed in period, Net Change, Peak Day Count; charts Total Rooms Over Time (stacked by site), Tier Distribution, Site Breakdown by Month, Rooms by Site & Tier, Room Changes Heatmap, Room Lifespan Timeline, Month-over-Month Changes, Room First Seen, Room Age; Room Details sortable table | P1 | Regression | Playwright | Not Tested
INS-011 | Consumption | Billing-relevant accuracy | 1. Cross-check Active Rooms + tier split against known tenancy subscription | Room counts and tier breakdown match billing records — this drives invoicing; flag any discrepancy as critical | P1 | Regression | Manual | Not Tested
INS-012 | Custom | ECU Custom Insight / INPOD | 1. Open tenant-custom insights | Custom dashboards render their configured panels; empty config shows clean page (title + range bar) without errors | P3 | Regression | Playwright | Not Tested
INS-013 | Permissions | Insights visibility by permission | 1. Login without Insights access | Insights section hidden; custom insights restricted to entitled groups | P1 | Regression | Manual | Not Tested
INS-014 | Data Accuracy | Panel values vs raw Elastic + v3 Kibana (rewrite) | 1. For each Insights panel, compare against direct ES query and v3.6 Kibana output 2. Validate metric-card calculations (percentages, averages, totals) | ARCHITECTURAL CHANGE: same Kibana->ECharts rewrite as Vitals. Counts, aggregation buckets, pie/bar proportions and computed metrics must match data-level, incl. empty/sparse data handling | P1 | Regression | Manual | Not Tested
INS-015 | Consumption | Consumption tab has no date controls | 1. Open Insights > Consumption | Date range controls intentionally hidden (showDateControls=false); data is full-period; other tabs keep range selector | P3 | Regression | Playwright | Not Tested
INS-016 | API | Batch search endpoint behaviour | 1. Exercise POST /api/insights/batch-search with multiple searches 2. Verify response keyed by search id with metadata (tenant, env, total_hits, aggregation_count) | Batch returns per-id results; partial failures surfaced per item; UI panels render from batch correctly | P2 | Regression | API | Not Tested
INS-017 | Custom | Custom Insights dashboards config-driven | 1. Configure custom dashboard for Insights; check /insights/{customId} route + ip-insights-custom permission | Custom tab renders; permission-gated; tab order follows tenant tabLabels | P2 | Regression | Manual | Not Tested

## Assets
Assets — Regression Tests
Asset Register (25k+), asset detail tabs, Actions schedule/history
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
AST-001 | List | Asset Register loads at scale | 1. Open Assets > Asset Register (tenancy ~25k assets) | Table renders within acceptable time; count label accurate (e.g. '25408 assets'); pagination stable; no browser freeze | P1 | Smoke | Playwright | Not Tested
AST-002 | List | Columns and sorting | 1. Inspect columns; sort by Name, Category, Brand | Columns Room, Name, Category, Brand, Model, IP Address, Power, Status, Compliance; sorting server-side across full dataset (not just current page) | P1 | Regression | Playwright | Not Tested
AST-003 | List | Search assets | 1. Search by asset name, model, room, IP | Matching rows returned across the full register; count updates; clear restores | P1 | Regression | Playwright | Not Tested
AST-004 | List | Saved views + column picker + export | 1. Save a filtered view; recall; export | Same machinery as Alerts (Recall/Save/Delete View); export contains filtered rows; large export runs as background op under bell | P2 | Regression | Playwright | Not Tested
AST-005 | List | Edit (bulk) mode | 1. Click Edit button 2. Modify an editable field (if enabled) 3. Save/cancel | Edit mode toggles; edits validate and persist; cancel discards; permission-gated | P2 | Regression | Manual | Not Tested
AST-006 | List | Row kebab View Details | 1. Click kebab on a row > View Details | Asset detail opens (/assets/detail/{roomId}/{assetId}) | P1 | Regression | Playwright | Not Tested
AST-007 | List | Power / Status / Compliance values | 1. Find assets with live status | Power shows On/Off/NA badge; Status reflects monitoring state; Compliance reflects policy evaluation; '-' for non-monitored | P2 | Regression | Manual | Not Tested
AST-008 | Detail | Detail tabs render | 1. Open an asset detail | Tabs Information, Status, Specifications, History, Alerts, Response Times, Files, Credentials, Actions all clickable; profile image or placeholder shown | P1 | Smoke | Playwright | Not Tested
AST-009 | Detail | Information tab completeness | 1. Open Information | GENERAL section: name, asset_id, room (name+id), zone, site, brand, model, category, system name/id, user_group, hostname, created_at/last_updated; CONNECTIVITY: ip_address. Sensitive fields (password) never shown in plaintext | P1 | Regression | Playwright | Not Tested
AST-010 | Detail | Status tab | 1. Open Status tab | Live status renders for monitored assets. KNOWN ISSUE (dev): crashes with 'e is not iterable' error boundary — must be fixed/regression-tested | P1 | Regression | Playwright | Not Tested
AST-011 | Detail | Specifications per asset profile | 1. Open Specifications on a profiled asset and an unprofiled one | Profiled: spec fields render; Unprofiled: 'No specifications available for this asset profile.' | P2 | Regression | Playwright | Not Tested
AST-012 | Detail | History / Alerts / Response Times tabs | 1. Open each tab on an actively monitored asset | History shows asset event log; Alerts lists alerts raised by this asset (click-through works); Response Times charts ping/poll latency | P2 | Regression | Manual | Not Tested
AST-013 | Detail | Files tab upload/download | 1. Open Files; upload a small file (dev); download it; delete it | Upload succeeds with progress; file listed with metadata; download intact; delete confirmed | P2 | Regression | Manual | Not Tested
AST-014 | Detail | Credentials tab security | 1. Open Credentials | Credentials masked by default; reveal/edit permission-gated; credentials_tainted flag surfaces when device rejects stored creds | P1 | Regression | Manual | Not Tested
AST-015 | Detail | Actions tab (ops actions) | 1. Open Actions on an asset whose profile defines ops actions 2. Trigger a safe action (e.g. Refresh Webpage) in DEV | Profile-defined actions listed; trigger executes and appears in Assets > Actions History and Insights > Ops; assets without actions show 'No actions available for this asset' | P1 | Regression | Manual | Not Tested
AST-016 | Actions Page | Schedule and History tabs | 1. Open Assets > Actions | Tabs Schedule ¦ History; table Status, Scheduled Time, Room, Asset, Category, Brand, Model, Action, Parameters, Type, Origin; empty state 'No scheduled actions'; export works | P2 | Regression | Playwright | Not Tested
AST-017 | Actions Page | Scheduled action lifecycle | 1. Schedule an action for future time (via automation or asset Actions) 2. Wait for execution | Appears under Schedule until execution; moves to History with outcome status; Origin distinguishes manual vs automation | P2 | Regression | Manual | Not Tested
AST-018 | Teams/Zoom | Specialised asset categories | 1. Open a Teams Room asset and (if present) Zoom Room asset detail | Category-specific data renders (e.g. Teams agent versions); no generic-template errors | P2 | Regression | Manual | Not Tested
AST-019 | Permissions | Asset management permission gating | 1. Login with read-only asset access | Edit/Files/Credentials/Actions mutations hidden or disabled; viewing allowed | P1 | Regression | Manual | Not Tested
AST-020 | Actions | Invoke action dialog with real-time progress | 1. Invoke an asset action (e.g. reboot/screenshot) 2. Watch WebSocket progress | LiveResponse messages (status/error/preview_image) stream to the dialog; active-job count badge shows in header; failures show error state | P1 | Regression | Manual | Not Tested
AST-021 | Credentials | Credentials dialog (Sight monitoring creds) | 1. Open credentials dialog with permission 2. View/copy/update credentials | Credentials masked by default, copy works, update persists (PUT /asset/credentials); credentials_tainted flag clears after successful update | P1 | Regression | Manual | Not Tested
AST-022 | Pagination | Server-side paginated v3 assets endpoint | 1. On 25k-asset registry: page through, change page size, sort server-side (POST /v3/assets) | Pagination/sort/search execute server-side (not client slice); response times acceptable; total count accurate | P1 | Regression | API | Not Tested
AST-023 | Files | Asset file upload/download via presigned URLs | 1. Upload file on asset Files tab; download it; check URL expiry | Presigned URL flow works (POST /asset/file, GET /asset/file); expired URLs fail gracefully; files listed with metadata | P2 | Regression | Manual | Not Tested

## Information
Information — Regression Tests
Custom room-information summary views and inline editing
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
INF-001 | Views | Custom views render as tabs | 1. Open Information page | Configured summary views render as tabs (e.g. Demo View, Room Summary, WebCheckout); first tab loads by default | P1 | Smoke | Playwright | Not Tested
INF-002 | Views | Per-view custom columns | 1. Switch between tabs | Each view shows its configured attribute columns (SLA, System ID, Timetable, Capture Device, area, Schematic PDF, etc.); horizontal scroll for wide sets; sortable | P1 | Regression | Playwright | Not Tested
INF-003 | Data | Attribute links work | 1. Click a Timetable URL and a Schematic PDF link | External links open in new tab (shorturl + S3 attachment links valid, no 403/404) | P2 | Regression | Manual | Not Tested
INF-004 | Edit | Inline edit (pencil) mode | 1. Click pencil icon 2. Edit an attribute value; save 3. Re-load page | Edit mode enables cell editing; saved value persists and is visible to other users; validation per attribute type (number/boolean/text) | P1 | Regression | Manual | Not Tested
INF-005 | Search | Search rooms within a view | 1. Type a room name | Rows filter live; works in every view tab | P2 | Regression | Playwright | Not Tested
INF-006 | Views | Saved views (Recall/Save) | 1. Apply search/sort; save view; recall | View machinery works as in other modules | P3 | Regression | Playwright | Not Tested
INF-007 | Sync | Attribute changes propagate | 1. Change a room attribute under Admin > Room Attributes (or via import) 2. Check Information view | Information view reflects new attribute values/columns; Summary Views config drives which tabs exist | P2 | Regression | Manual | Not Tested
INF-008 | Permissions | Information access gating | 1. Login without Room Information permission | Information nav hidden; URLs denied; edit mode requires elevated permission | P1 | Regression | Manual | Not Tested
INF-009 | Edit Rules | Field editability matrix | 1. Attempt inline edit on: Hyperlink, File, Image fields; smart attributes; sync_direction=Inbound fields; dynamic fields; plain text/enum fields | Only non-Hyperlink/File/Image, non-smart, non-Inbound, non-dynamic fields are editable; enum fields show dropdown of enum values; others read-only with no edit affordance | P1 | Regression | Playwright | Not Tested
INF-010 | Links | SecureLinks flag behaviour | 1. Tenant with InformationDetailView.SecureLinks=true: open Files/Links section | Links served as secured/presigned (POST /smp/download_files); without flag, direct URLs; no broken links either way | P2 | Regression | Manual | Not Tested
INF-011 | Sections | Config-driven sections (Digital Signage / Web Checkout) | 1. Toggle showDigitalSignage/showWebCheckout in tenant config 2. Open information detail | Sections render only when configured; Web Checkout uses v1 API endpoints incl. sync (POST /room/{id}/webcheckout/sync); Timetable section appears only when timetable fields detected | P2 | Regression | Manual | Not Tested
INF-012 | Export | Room fields CSV export request flow | 1. Trigger CSV export (POST /smp/roomfields/csv/request) 2. Wait for completion | Async export tracked (bell PROGRESS); file matches current view's rooms/fields; filename convention {tenant}-{date}-{type}.csv | P2 | Regression | Manual | Not Tested

## Integrations
Integrations — Regression Tests
QSC Q-Sys, Microsoft Teams Room, Appspace
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
ITG-001 | Q-Sys | Global Logs tab | 1. Open Integrations > QSC Q-Sys | Tabs Global Logs ¦ Global Events ¦ Global Vitals; logs table (Date & Time, Room Name, Device IP, Message, Category, Source) with time-range selector (Last 1 Day) and saved views; 'No logs found' empty state | P1 | Smoke | Playwright | Not Tested
ITG-002 | Q-Sys | Global Events tab | 1. Click Global Events | Events table (… Category, Severity) renders; search + export work; events correspond to Q-Sys cores in environment | P2 | Regression | Playwright | Not Tested
ITG-003 | Q-Sys | Global Vitals tab | 1. Click Global Vitals | KPIs Q-SYS Devices / Total Faults / Total Warnings; charts CPU Usage %, Memory Usage %, Disk Usage %, CPU Temperature, Faults over Time, Warnings over Time; values match connected cores; clean empty states when none | P2 | Regression | Playwright | Not Tested
ITG-004 | Q-Sys | Time range selector | 1. Change 'Last 1 Day' range | Logs/events/vitals re-query for window | P2 | Regression | Playwright | Not Tested
ITG-005 | Teams Room | Device List | 1. Open Integrations > Microsoft Teams Room | Tabs Device List ¦ Insights; table Microsoft Teams Room Name, Model, IP, MAC, Serial Number, Teams Admin Agent, Windows OS, Teams App, Activity State, Health Status (HEALTHY badge); device data matches Teams Admin Center | P1 | Regression | Playwright | Not Tested
ITG-006 | Teams Room | Insights tab | 1. Click Insights tab | Teams Room analytics render (usage/health) without errors | P2 | Regression | Manual | Not Tested
ITG-007 | Appspace | Appspace page loads its own module | 1. Click Appspace in sidebar 2. Also deep-link /integrations/appspace directly | Appspace integration UI renders (devices/content health). KNOWN ISSUE: deep link and even sidebar nav currently render the QSC Q-Sys module — regression-test the route fix | P1 | Regression | Playwright | Not Tested
ITG-008 | Routing | Integration deep links after refresh | 1. On each integration page press F5 | Page reloads to the same integration (not Q-Sys); breadcrumb/title correct | P1 | Regression | Playwright | Not Tested
ITG-009 | Permissions | Integrations visibility by permission | 1. Login without integration management permission | Integrations section hidden; URLs denied | P1 | Regression | Manual | Not Tested
ITG-010 | Config | Integration with no configured connection | 1. View an integration page in a tenancy without that integration configured | Clean empty/CTA state, no stack traces | P2 | Edge | Manual | Not Tested
ITG-011 | Parity | Cisco Webex / Zoom / Biamp SageVue presence (v3 parity) | 1. v3 shipped Webex, Zoom, Biamp SageVue integrations; v4 permission constants exist (ip-integrations-cisco-webex/zoom/biamp-sagevue) 2. Check v4 tabs for tenants using them | PARITY CHECK: integrations render for entitled tenants or the gap is documented as accepted delta in the parity catalogue | P1 | Regression | Manual | Not Tested
ITG-012 | MTR | MTR data + actions flag | 1. Open MTR tab (devices/insights/properties endpoints) 2. Tenant with mtr_actions_enabled=true: verify device actions | Device list matches Teams admin data; insights/properties load; MTR actions appear only when alertConfig.mtr_actions_enabled | P2 | Regression | Manual | Not Tested
ITG-013 | Q-Sys | Per-subtab Q-Sys permissions | 1. Grant only ip-integrations-qsc-logs (not vitals/events) 2. Open Q-Sys page | Only Logs subtab visible; Vitals/Events hidden per ip-integrations-qsc-vitals/-events permissions | P2 | Regression | Manual | Not Tested
ITG-014 | Appspace | Appspace endpoints listing | 1. Open Appspace tab (GET /integrations/appspace + /endpoints) | Appspace devices/endpoints render; empty state when unconfigured; (blocked today by route-rendering bug BUG-002) | P2 | Regression | Playwright | Not Tested

## Rooms
Rooms — Regression Tests
Rooms list and room support view
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
ROM-001 | List | Rooms list loads under All Sites | 1. Open Rooms | List loads within 30s budget; 'POWERED ON: n' badge + total room count accurate. KNOWN ISSUE (dev): 'Failed to load rooms — timeout of 30000ms exceeded' with Retry; must be perf-tested at production scale | P1 | Smoke | Playwright | Not Tested
ROM-002 | List | Columns and default sort | 1. Inspect table | Columns Room, Zone, Site, Power, Type, Alerts; default sorted by Alerts desc; all columns sortable | P1 | Regression | Playwright | Not Tested
ROM-003 | List | Search rooms | 1. Search a room name | Filtered server-side promptly; count and POWERED ON badge update for the filtered set | P1 | Regression | Playwright | Not Tested
ROM-004 | List | Retry after load failure | 1. If load fails, click Retry | Retry re-issues the query; succeeds when backend healthy; no duplicated rows | P2 | Negative | Playwright | Not Tested
ROM-005 | List | Saved views / column picker / export | 1. Save a view, recall it, export | Standard view machinery works; export matches filter | P2 | Regression | Playwright | Not Tested
ROM-006 | Support View | Room support view opens | 1. Click a room row (or room link from an alert/asset) | Room support view opens with room header (power/occupancy state) and tabs for Hotlist, Assets, History, Resources, Schedule (per v4 design); breadcrumb back to Rooms | P1 | Smoke | Playwright | Not Tested
ROM-007 | Support View | Room Hotlist tab | 1. Open room's Hotlist tab | Only this room's active alerts listed; claiming/resolving here reflects in global Hotlist | P1 | Regression | Playwright | Not Tested
ROM-008 | Support View | Room Assets tab + live status | 1. Open Assets tab 2. Open an asset's live status | All room assets listed with category/status; live status streams current device state for online assets | P1 | Regression | Manual | Not Tested
ROM-009 | Support View | Room History tab | 1. Open History tab | Room event history (power, occupancy, alerts) in chronological order; filters work | P2 | Regression | Manual | Not Tested
ROM-010 | Support View | Room Resources tab | 1. Open Resources tab | Room resources/attachments (schematics, docs) listed and downloadable | P2 | Regression | Manual | Not Tested
ROM-011 | Support View | Room Schedule tab | 1. Open Schedule tab on a calendar-integrated room | Upcoming bookings render from calendar integration; correct timezone | P2 | Regression | Manual | Not Tested
ROM-012 | Support View | Ellipsis/kebab room actions | 1. Open room kebab menu | Room-level actions (e.g. maintenance mode, edit info) listed per permissions; maintenance toggle suppresses room alerts and shows in Vitals > Rooms maintenance count | P1 | Regression | Manual | Not Tested
ROM-013 | Cross-link | Room links from other modules | 1. Click room name from Alert detail, Asset register, Dashboard Top Alerting Rooms | Each opens the same room support view. KNOWN ISSUE: alert-detail room button currently no-op | P2 | Regression | Playwright | Not Tested
ROM-014 | Maintenance | In-maintenance room behaviour | 1. Put a room in maintenance (dev) 2. Trigger an alert on its assets | Alerts suppressed (appear under SUPPRESSED with maintenance context); Vitals Rooms maintenance count +1; SLA tracking respects maintenance window | P1 | Regression | Manual | Not Tested
ROM-015 | Permissions | Rooms visibility by permission/user group | 1. Login as user scoped to a user group | Only rooms in the user's group(s) listed; counts scoped accordingly | P1 | Regression | Manual | Not Tested
ROM-016 | Launchpad | Launchpad panel: all launcher types | 1. On a room with each resource type, test: Web Panels (direct URL), XPanels (launch URL API), VNC (host:port), Cameras, Timetable/Schedule popups, Recorders (echo360/capture/recorder fields) | Each launcher opens its target; XPanel uses GET /room/{id}/xpanels/{name}/launchurl; monitoring-zone rooms use the zone-aware monitoring launch URL (v3: monitoring- prefix) — verify v4 handles both origins | P1 | Regression | Manual | Not Tested
ROM-017 | Live Status | Live status bar fields via WebSocket | 1. Open room detail of an active room 2. Change room state (occupancy, lights, volume, start recording, present a source) | Status bar live-updates: Occupied/Vacant, Maintenance, Recording + upcoming recording, Lights, Presenting sources, Volume/Program level, Mics — without page refresh | P1 | Regression | Manual | Not Tested
ROM-018 | Maintenance | Set/Clear maintenance with notes | 1. Set maintenance with a note (PUT /room/{id}/maintenance) 2. Clear it (DELETE) | Maintenance state propagates: alerts suppressed, Vitals maintenance count, status bar badge; notes recorded; clear restores monitoring | P1 | Regression | Playwright | Not Tested
ROM-019 | Schedule | Schedule panel + week modal + calendaring flag | 1. Open schedule panel on calendar-integrated room; open week modal 2. Check a tenant with rooms calendaring disabled | Meetings render (GET /room/{id}/meetings) with correct timezone; week modal shows full week; panel hidden/disabled when calendaring not enabled | P2 | Regression | Manual | Not Tested
ROM-020 | Layout | Panel order from tenant config | 1. Change uiSettings.Rooms.RoomSupportViewPanelOrder 2. Reload room detail | Panels reorder per config (default schedule, launchpad, information, resources); Assets and Hotlist panels remain fixed | P3 | Regression | Manual | Not Tested
ROM-021 | Permissions | Launch Remote UI permission | 1. User without ip-rooms-launch-remote-ui opens room detail | Remote UI launcher hidden/disabled; with permission, remote URL (remote.{tenant}.{domain}?roomid=...) opens | P2 | Regression | Manual | Not Tested

## Axis AI
Axis AI — Regression Tests
Axis AI chat, saved insights, data scoping
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
AXI-001 | Chat | Landing state | 1. Open Axis AI | Chat tab active; CONNECTED badge; welcome message + example prompt buttons; input with send button | P1 | Smoke | Playwright | Not Tested
AXI-002 | Chat | Example prompt buttons | 1. Click 'What rooms have alerts?' | Prompt submitted; Axis responds with data consistent with Hotlist (rooms with active alerts) | P1 | Regression | Manual | Not Tested
AXI-003 | Chat | Natural language data query with visualisation | 1. Ask 'Show me the alert trend over the last two months' | Response includes a rendered chart/table; values consistent with Insights > Alerts | P1 | Regression | Manual | Not Tested
AXI-004 | Chat | Slash commands and /axis-catalog | 1. Type '/' in input 2. Run /axis-catalog | Slash command menu appears; /axis-catalog lists available datasets and preset questions | P2 | Regression | Playwright | Not Tested
AXI-005 | Chat | Nonsense/out-of-scope question | 1. Ask something unrelated (e.g. weather) | Graceful refusal/redirect to platform data scope; no crash or hallucinated tenant data | P2 | Negative | Manual | Not Tested
AXI-006 | Chat | Clear conversation | 1. Click trash icon top-right | Conversation clears back to welcome state (with confirm if destructive) | P3 | Regression | Playwright | Not Tested
AXI-007 | Saved Insights | Save and recall an insight | 1. Generate a chart answer 2. Save it 3. Open Saved Insights tab | Saved item listed with name/date; reopening re-renders the visualisation; delete works | P2 | Regression | Manual | Not Tested
AXI-008 | Security | Data scoping in AI answers | 1. Ask for data as a user-group-restricted user | Responses only include rooms/devices within the user's permission scope — no leakage across user groups/tenants | P1 | Regression | Manual | Not Tested
AXI-009 | Resilience | AI service disconnected | 1. Open Axis AI when backend unavailable (dev simulation) | Status badge reflects disconnected; input disabled or queued with clear messaging | P3 | Edge | Manual | Not Tested
AXI-010 | Persistence | Saved insights caps + in-memory store limits | 1. Save >50 insights; append >200 query-log entries 2. Restart BFF (dev) | Caps enforced (50 insights deduped by messageId, 200 log entries); KNOWN LIMITATION: store is in-memory per user — data lost on BFF restart; verify behaviour is acceptable/documented before GA | P2 | Edge | API | Not Tested
AXI-011 | Connection | Connection state machine | 1. Observe badge states: connected / disconnected / reconnecting / service_unavailable (kill WS, restore) | Status badge transitions correctly; reconnect recovers; queries blocked or queued while disconnected with clear messaging | P2 | Regression | Manual | Not Tested
AXI-012 | Replay | Query replay from saved insight | 1. Save an insight; open Saved Insights; click replay | Original query re-submitted into chat (pendingQuery), new response generated; usage logged to query-log | P3 | Regression | Manual | Not Tested

## Administration
Administration — Regression Tests
Audit logs, asset profiles/drivers/policies, settings, users, room attributes, import/export, automation, incident rules
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
ADM-001 | Audit Logs | Audit logs page loads | 1. Open Administration > Audit Logs | Log table with filters loads. KNOWN ISSUE (dev): crashes 'A <Select.Item /> must have a value prop that is not an empty string' — regression-test the fix; verify error boundary resets when navigating away (currently sticks until Try again) | P1 | Regression | Playwright | Not Tested
ADM-002 | Audit Logs | Actions are audited | 1. Claim an alert, edit an attribute, sign in/out 2. Check audit logs | Each action recorded with actor, timestamp, entity and action type; filterable by user/date/type | P1 | Regression | Manual | Not Tested
ADM-003 | Assets Admin | Asset profile tabs render | 1. Open Administration > Assets | Tabs Asset Profiles ¦ Space VC Drivers ¦ Space CE Drivers ¦ Sight Drivers ¦ Ops Actions ¦ Pulse Drivers ¦ Asset Policies ¦ Asset Fields; profile table columns Profile Name, Type, Brand, Model, ID Convention, Name Convention | P1 | Smoke | Playwright | Not Tested
ADM-004 | Assets Admin | Create asset profile | 1. Click + Create Profile 2. Complete and save (dev) | Profile created and listed; assets matching ID convention pick up profile (specs/actions become available on asset detail) | P1 | Regression | Manual | Not Tested
ADM-005 | Assets Admin | Driver tabs (Space VC/CE, Sight, Pulse) | 1. Open each driver tab | Driver lists render with version/status; create/edit driver config flows validate required fields | P2 | Regression | Manual | Not Tested
ADM-006 | Assets Admin | Ops Actions definitions | 1. Open Ops Actions tab 2. Create/edit an action (dev) | Action defined with parameters; becomes triggerable from matching assets' Actions tab and Automation policies | P2 | Regression | Manual | Not Tested
ADM-007 | Assets Admin | Asset Policies (compliance) | 1. Open Asset Policies 2. Define a policy (e.g. DHCP must be disabled) | Policy evaluation flags non-compliant assets (Compliance column in register) and raises Policy Compliance alerts (cf. 'DHCP Enabled is True' demo alert) | P1 | Regression | Manual | Not Tested
ADM-008 | Assets Admin | Asset Fields (custom fields) | 1. Open Asset Fields; add a custom field | Field appears on asset records; values editable and exportable | P2 | Regression | Manual | Not Tested
ADM-009 | Settings | Change Mode toggle | 1. Open Administration > Settings 2. Enable Change Mode | Toggle persists; SLA tracking halted during change window (outages excluded from SLA metrics); banner/indicator communicates active change mode; disable restores tracking | P1 | Regression | Manual | Not Tested
ADM-010 | Settings | ServiceNow Auto Incident Creation toggle | 1. Toggle the setting | When ON: SN incidents auto-create/resolve 15 min after alert create/resolve. When OFF: no automatic SN incidents | P1 | Regression | Manual | Not Tested
ADM-011 | Users | Users tab listing | 1. Open Administration > Users | Tabs Users ¦ User Groups ¦ Roles ¦ SAML Roles ¦ App Clients; user table: Given/Family Name, Email, Roles, User Group, SSO Provider, Date Created, Terms (accepted?); search + export | P1 | Smoke | Playwright | Not Tested
ADM-012 | Users | Create/edit user and assign roles | 1. Create a test user (dev); assign role + user group | User created; receives access per role on next login; edits audited | P1 | Regression | Manual | Not Tested
ADM-013 | Users | User Groups CRUD + room scoping | 1. Open User Groups tab 2. Create group; attach rooms/users | Group scopes data visibility (rooms/alerts/assets) for members; deletion blocked or warned when in use | P1 | Regression | Manual | Not Tested
ADM-014 | Users | Roles tab + custom roles | 1. Open Roles 2. Create custom role with limited permissions | Permission matrix saved; members see only granted modules (see RBAC sheet) | P1 | Regression | Manual | Not Tested
ADM-015 | Users | SAML Roles mapping | 1. Open SAML Roles 2. Map an IdP group to a portal role | SSO users receive mapped roles on login; unmapped users get default/no access | P2 | Regression | Manual | Not Tested
ADM-016 | Users | App Clients (API credentials) | 1. Open App Clients 2. Create a client; copy secret | Client ID/secret issued once; scoped API access works; revoke invalidates immediately | P2 | Regression | Manual | Not Tested
ADM-017 | Room Attributes | Smart Room Attributes list | 1. Open Administration > Room Attributes | Tabs Smart Room Attributes ¦ Summary Views; table Attribute Name, Type (BOOLEAN/NUMBER/TEXT badges), Grouping, Source (configuration/information/configuration_space), Conditions count; search + export; count label accurate (e.g. 28 attributes) | P1 | Smoke | Playwright | Not Tested
ADM-018 | Room Attributes | Create attribute with conditions | 1. + Create Attribute; define type/grouping/source + condition(s) | Attribute saved; conditions evaluated against rooms; surfaced in Information views and room support view | P1 | Regression | Manual | Not Tested
ADM-019 | Room Attributes | Duplicate attribute names | 1. Create attribute with an existing name (e.g. 'Camera Input' duplicates exist in dev) | System prevents/warns on duplicates or handles them deterministically — current dev data shows duplicates; clarify expected behaviour | P2 | Edge | Manual | Not Tested
ADM-020 | Room Attributes | Summary Views builder | 1. Open Summary Views tab 2. Create/edit a view with chosen attributes | View appears as a tab on the Information page with configured columns | P1 | Regression | Manual | Not Tested
ADM-021 | Import/Export | Data Import rules list | 1. Open Administration > Import / Export | Tabs Data Import ¦ Data Export; rules table: Dynamic Field, Filename, Format (CSV), Name Path, Value Path; search + Create Rule + Manual Import buttons | P1 | Smoke | Playwright | Not Tested
ADM-022 | Import/Export | Manual CSV import | 1. Click Manual Import 2. Upload a valid CSV matching a rule | Import processed; progress under bell PROGRESS tab; imported values appear on rooms (dynamic fields); result summary shows rows ok/failed | P1 | Regression | Manual | Not Tested
ADM-023 | Import/Export | Import with malformed CSV | 1. Upload CSV with wrong headers/empty values | Validation errors reported under ERRORS tab with row detail; no partial corruption of room data | P1 | Negative | Manual | Not Tested
ADM-024 | Import/Export | Create import rule | 1. Create Rule mapping name path/value path | Rule saved and applied to subsequent imports of that filename | P2 | Regression | Manual | Not Tested
ADM-025 | Import/Export | Data Export tab | 1. Open Data Export 2. Run an export | Export generated and downloadable; progress visible; file contents match selected dataset | P2 | Regression | Manual | Not Tested
ADM-026 | Automation | Policies list | 1. Open Administration > Automation | Policies table: Policy Name, Asset (profile), Filters, Conditions, Actions, Trigger Time, Enabled checkbox; search + Create Policy | P1 | Smoke | Playwright | Not Tested
ADM-027 | Automation | Create policy with schedule trigger | 1. + Create Policy: pick asset profile, condition (e.g. brightness), action (Refresh Webpage), schedule (e.g. Weekday mornings 05:00 Mon-Fri) 2. Enable | Policy saved; fires at schedule; execution visible in Insights > Ops Trigger History as user 'Automation' and in Assets > Actions History | P1 | Regression | Manual | Not Tested
ADM-028 | Automation | ASAP trigger policy | 1. Create policy with Trigger Time ASAP on a condition 2. Make condition true (dev) | Action fires promptly when condition met; does not loop infinitely (cooldown respected) | P1 | Regression | Manual | Not Tested
ADM-029 | Automation | Enable/disable toggle | 1. Untick Enabled on a policy | Disabled policy stops firing; toggle state persists; audit logged | P1 | Regression | Playwright | Not Tested
ADM-030 | Automation | Policy filters (room scoping) | 1. Create policy with filter room_name = specific room | Policy only affects matching room's assets | P2 | Regression | Manual | Not Tested
ADM-031 | Incidents Admin | Incident Rules list | 1. Open Administration > Incidents | Incident Rules table: Enabled toggle, Incident Name, Priority (1-10), Severity (Low+/Medium+/High+), Qty (1+/20+), Scope (Room/Zone/Global), Impact, Urgency; search + Create Rule | P1 | Smoke | Playwright | Not Tested
ADM-032 | Incidents Admin | Create incident rule and trigger | 1. Create rule (e.g. Severity High+, Qty 1+, Scope Room, Impact High, Urgency Medium) 2. Raise matching alert(s) | Incident auto-created with rule's impact/urgency-derived priority; scope aggregation correct (Global rule groups across rooms; Room rule one per room) | P1 | Regression | Manual | Not Tested
ADM-033 | Incidents Admin | Rule priority ordering | 1. Create overlapping rules with different Priority values | Lower/higher priority number wins per spec (confirm expected precedence); only one incident created per event set | P2 | Edge | Manual | Not Tested
ADM-034 | Incidents Admin | Disable rule stops creation | 1. Disable a rule; raise matching alerts | No incident created while disabled | P1 | Regression | Manual | Not Tested
ADM-035 | Automation | Action Macros CRUD | 1. Automation > Action Macros: create a macro (reusable action set); edit; delete | Macro CRUD persists (/automation/macros); macros selectable from automation policies; delete blocked/warned if referenced | P1 | Regression | Manual | Not Tested
ADM-036 | Automation | Change Freezes CRUD + alert flag | 1. Create a change freeze window covering now 2. Inspect alerts raised during the freeze | Freeze CRUD works (/automation/change_freezes); alerts during freeze carry change_mode context; automation actions blocked during freeze | P1 | Regression | Manual | Not Tested
ADM-037 | Automation | Maintenance Windows CRUD (timezone-aware) | 1. Create maintenance window in a non-UTC timezone incl. across DST 2. Verify suppression during the window | Window times honour configured timezone (v3 used moment-tz local->UTC conversion); alerts suppressed within window; resume after | P1 | Regression | Manual | Not Tested
ADM-038 | Settings | Incident setting visibility coupled to ticketing | 1. Tenant with alertConfig.ticketing=false: open Settings | ServiceNow Auto Incident Creation toggle hidden when ticketing disabled; visible+functional when enabled; Change Mode always present with confirm dialog | P2 | Regression | Manual | Not Tested
ADM-039 | Users | App client secret shown once | 1. Create app client; capture secret; close dialog; reopen client | Secret displayed exactly once at creation; not retrievable later; delete revokes immediately (auth fails) | P1 | Regression | Manual | Not Tested
ADM-040 | Audit | Login/logout audit events | 1. Login and logout (POST /user/login, /user/logout fired) 2. Check Audit Logs | Both events recorded with user, timestamp, session; visible in admin audit log with filters | P2 | Regression | Playwright | Not Tested

## RBAC & Permissions
RBAC & Permissions — Regression Tests
Role/permission visibility, user-group scoping, server-side enforcement
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
RBC-001 | Module Visibility | Hotlist access permission | 1. Create role without Hotlist Access; login as member | Hotlist (Alerts+Incidents) hidden from nav; /hotlist/* URLs denied; dashboard alert widgets hidden or masked | P1 | Regression | Manual | Not Tested
RBC-002 | Module Visibility | Vitals dashboard permission | 1. Role without Vitals access | Vitals section hidden; direct URLs denied | P1 | Regression | Manual | Not Tested
RBC-003 | Module Visibility | Insights dashboard permission | 1. Role without Insights access | Insights hidden incl. custom insights | P1 | Regression | Manual | Not Tested
RBC-004 | Module Visibility | Asset management permission | 1. Role without Asset Management | Assets section hidden; asset URLs denied; asset links from alerts show permission message | P1 | Regression | Manual | Not Tested
RBC-005 | Module Visibility | Room information permission | 1. Role without Room Information | Information page hidden | P1 | Regression | Manual | Not Tested
RBC-006 | Module Visibility | Room management permission | 1. Role without Room Management | Rooms page hidden; room support view inaccessible | P1 | Regression | Manual | Not Tested
RBC-007 | Module Visibility | Integrations management permission | 1. Role without Integrations access | Integrations section hidden | P1 | Regression | Manual | Not Tested
RBC-008 | Module Visibility | Administration access permission | 1. Role without Administration access | System > Administration hidden; /admin/* denied | P1 | Regression | Manual | Not Tested
RBC-009 | Custom Access | Custom (granular) permission set | 1. Create custom role: read-only Hotlist + Vitals only | Member sees exactly those modules; mutation actions (claim/resolve/create) hidden or rejected server-side | P1 | Regression | Manual | Not Tested
RBC-010 | Custom Access | Server-side enforcement (API) | 1. As restricted user, replay an admin API call (claim alert / create incident) via devtools | API rejects with 403 — UI hiding is not the only gate | P1 | Regression | Manual | Not Tested
RBC-011 | User Groups | User group data scoping | 1. Assign user to one user group; login | Alerts/Assets/Rooms/Insights restricted to that group's rooms; User Group selector limited to permitted groups | P1 | Regression | Manual | Not Tested
RBC-012 | User Groups | Filtered view custom access | 1. Grant role access to specific saved/filtered views only | User sees only permitted views in Recall View and Information tabs | P2 | Regression | Manual | Not Tested
RBC-013 | Escalation | Permission change takes effect | 1. Change a user's role while they are logged in | New permissions apply on next navigation/login per spec; revoked module disappears; no stale access after re-auth | P2 | Regression | Manual | Not Tested
RBC-014 | Terms | Revoked terms re-acceptance | 1. Reset terms acceptance for a user (admin) | User is re-prompted with Terms popup at next login and blocked until accepted | P2 | Edge | Manual | Not Tested
RBC-015 | Room Manager | Cross-app permission consistency | 1. Check Room Manager access via apps grid for restricted user | Room Manager respects its own admin/room/template access permissions; portal grid still lists the app but access is gated in-app | P2 | Regression | Manual | Not Tested
RBC-016 | Granular | Severity-level + per-tab permission matrix | 1. Exercise the granular constants: severity-level alert perms, per-tab Vitals (incl. compliance/custom), per-tab Insights, Q-Sys subtab perms, integrations per-vendor perms | Each permission independently gates exactly its surface (~50+ constants in src/config/permissions.ts must match backend names); no orphan permissions | P1 | Regression | Manual | Not Tested
RBC-017 | Views | Saved-view permissions per module | 1. Role without ip-hotlist-save-view / -delete-view / ip-filteredview-*-edit 2. Try saving/deleting/editing views in each module | Save/Delete View controls hidden or rejected per-module; recall of existing views still allowed where view permission exists | P2 | Regression | Manual | Not Tested
RBC-018 | BFF | BFF performs token-validity only — backend must enforce RBAC | 1. With a valid token of a restricted user, call privileged BFF endpoints directly (e.g. POST /api/role, /api/alerts/purge) | SECURITY: BFF has NO per-endpoint RBAC (verified in code) — the platform backend MUST return 403; if any privileged endpoint succeeds, raise CRITICAL defect | P1 | Negative | API | Not Tested
RBC-019 | Filters | User-group + site (campus) scoping across modules | 1. As group-scoped user verify Hotlist, Vitals, Insights, Information, Rooms all re-query on group/site change | v3 used userAvailableGroups/Campuses with reload triggers; v4 site/group filters live in query keys — every module refetches; no module shows unscoped data | P1 | Regression | Manual | Not Tested

## RM-Portal Consistency
RM-Portal Consistency — Regression Tests
Room Manager (admin.dev) is source of truth: non-Parking-Lot rooms/devices must coincide with Portal rooms/assets. Baseline 10/06/2026: 678 RM rooms, 7 Parking Lot, expected Portal = 671
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
SYN-001 | Room Reconciliation | Non-Parking-Lot room count matches Portal | 1. Room Manager (RM): note total rooms and rooms with Zone = Parking Lot (Zone column filter) 2. Portal: note total room count (Rooms page / Vitals > Rooms / Consumption Active Rooms) | Portal room count = RM total - Parking Lot count (baseline 10/06/2026: 678 - 7 = 671). Any drift is a sync defect | P1 | Regression | API | Not Tested
SYN-002 | Room Reconciliation | Room-by-room name/ID parity | 1. Export RM room list (per-zone) 2. Export Portal rooms (or query API) 3. Diff on room_id | Every non-Parking-Lot RM room exists in Portal with identical Room ID (e.g. RM 'chatswoodl17bhr05s5' = Portal room_id) and name; Portal has no rooms missing from RM | P1 | Regression | API | Not Tested
SYN-003 | Room Reconciliation | Parking Lot rooms absent from Portal | 1. List the Parking Lot rooms in RM (7 as of baseline) 2. Search each name in Portal Rooms, Asset Register, Hotlist and Information | No Parking Lot room appears anywhere in Portal: no room entry, no assets, no alerts, no vitals/insights contribution | P1 | Regression | Playwright | Not Tested
SYN-004 | Room Lifecycle | New room deployed in RM appears in Portal | 1. RM: Add New Room (non-Parking-Lot zone), configure minimal template, Deploy 2. Wait for sync 3. Check Portal Rooms/Assets | Room appears in Portal with its devices as assets within the sync SLA; zone/site/user group carried over | P1 | Regression | Manual | Not Tested
SYN-005 | Room Lifecycle | Room moved OUT of Parking Lot reappears in Portal | 1. RM: move the room back to an active zone; Deploy | Room and devices reappear in Portal with monitoring resumed; no duplicate room entries created | P1 | Regression | Manual | Not Tested
SYN-006 | Room Lifecycle | Room deleted in RM is removed from Portal | 1. RM: delete a disposable test room (Options menu) 2. Check Portal | Room and all its assets disappear from Portal; historical alerts/audit remain queryable but room is not listed as active | P2 | Regression | Manual | Not Tested
SYN-007 | Device Reconciliation | Room devices match Portal assets (spot check) | 1. RM: open room > Configuration > Devices; note Control + Monitoring devices (name, driver, IP) 2. Portal: Asset Register filtered to that room | Portal assets = RM Control + Monitoring devices for the room — same names, IPs and categories. Baseline example: Chatswood-L17B-HR05-S5 has Decoder 3 (AMX, 192.168.1.0), Display 4 (NEC LCD, cloud-host), PDU 3 (APC, 192.168.1.2). NOTE: Portal currently shows suppressed alerts for 'Display 1' in this room — verify whether stale asset exists in Portal that is no longer in RM (drift!) | P1 | Regression | API | Not Tested
SYN-008 | Device Reconciliation | Tenancy-wide device-count reconciliation | 1. RM: Download CSV of devices per room (or API export across all non-Parking-Lot rooms) 2. Portal: export full Asset Register 3. Diff by asset_id/room_id | Asset sets match 1:1 (excluding Portal-only synthetic assets, if any — document them); no orphan Portal assets pointing to RM-deleted devices, no RM devices missing in Portal | P1 | Regression | API | Not Tested
SYN-009 | Device Lifecycle | Device added in RM appears as Portal asset | 1. RM: room > Devices > Add Device + (Control or Monitoring), Deploy 2. Check Portal Asset Register for the room | New asset appears with correct name/category/IP after sync; monitoring (Pulse/Sight) starts per driver type | P1 | Regression | Manual | Not Tested
SYN-010 | Device Lifecycle | Offline-group devices are not monitored | 1. RM: move a device to the Offline group; Deploy | Portal stops alerting for the device (define: hidden vs shown-as-offline); no 'Endpoint Responding' false alarms from intentionally offline kit | P2 | Regression | Manual | Not Tested
SYN-011 | Flags | Maintenance checkbox suppresses Portal alerts | 1. RM: tick Maintenance on a room; Deploy 2. Trigger an alert on that room's devices | Portal suppresses alerts for the room ('In Maintenance' context shown on suppressed rows); Vitals > Rooms maintenance count +1; unticking resumes normal alerting | P1 | Regression | Manual | Not Tested
SYN-012 | Metadata Sync | Zone / Site / User Group parity | 1. Compare Zone, Site, User Group of 10 sample rooms in RM vs Portal (room details, asset info, filters) | Values identical; Portal site filter and user-group scoping behave per RM assignment; changes in RM propagate on deploy | P1 | Regression | API | Not Tested
SYN-013 | Metadata Sync | Room rename propagates | 1. RM: rename a test room; Deploy | Portal room/asset records show new name; alert history links remain intact (no broken references) | P2 | Edge | Manual | Not Tested
SYN-014 | Teams Rooms | Microsoft Teams Rooms parity | 1. RM: open 'Microsoft Teams Rooms' panel (button top-right, badge count) 2. Portal: Integrations > Microsoft Teams Room device list | Device sets and health states coincide (RM badge count vs Portal device count); MTR devices excluded from Parking-Lot-style hiding rules unless room parked | P2 | Regression | Manual | Not Tested
SYN-015 | Control Links | Web Panel / VNC control links | 1. RM rooms list: click Web Panel / VNC links on a Space CE/VC room | Control surfaces open and connect to the same room instance the Portal monitors (sanity: same IPs/host as Portal asset details) | P2 | Regression | Manual | Not Tested
SYN-016 | Cross-Portal | v3 portal vs v4 portal data parity | 1. Old portal (portal.dev.../home): note room count, a sample room's assets and active alert count 2. v4 portal: same checks | Both portals (while v3 remains live) show the same underlying rooms/assets/alerts for the tenancy — they consume the same source of truth | P2 | Regression | Manual | Not Tested
SYN-017 | Negative | Undeployed RM changes do NOT appear in Portal | 1. RM: edit room config / add device but do NOT Deploy (or Revert Configuration) | Portal continues to show last-deployed state; Revert Configuration discards pending changes and Portal is unaffected | P2 | Negative | Manual | Not Tested
SYN-018 | Negative | Duplicate room IDs prevented across systems | 1. RM: attempt to create a room whose Room ID matches an existing (incl. Parking Lot) room | RM blocks duplicate IDs; Portal never receives two rooms with the same room_id | P2 | Negative | Manual | Not Tested
SYN-019 | Lifecycle | Hot reload (portable) live update path | 1. RM: on a Space VC room with Hot Reload Possible, make a config change using hot_reload=true 2. Check portal | Hot-reload changes apply to the live room without full redeploy and reflect in Portal data after sync; non-hot-reload changes require deploy | P2 | Regression | Manual | Not Tested
SYN-020 | Sight | Sight tier + inhibit_sight propagation | 1. RM: set room sight_tier (Sight/Sight+/Sight++); set inhibit_sight on one device; deploy 2. Portal: check Sight vitals/insights coverage | Sight monitoring intensity follows tier; inhibit_sight device excluded from Sight metrics while other devices report; shadow devices handled per driver capability | P2 | Regression | Manual | Not Tested
SYN-021 | UC | Teams/Zoom association sync | 1. RM: associate a room to a Teams room (uc_rooms assignment writes teams_id/teams_admin_agent) and/or zoom_id; deploy 2. Portal: Integrations > MTR (and Zoom if present) | Associated rooms appear in the portal integration device lists; dissociation removes them; IDs match | P2 | Regression | Manual | Not Tested
SYN-022 | Zones | Information-only zones cannot host production rooms | 1. RM: attempt to create a room in a zone flagged information_only | RM blocks creation (UI validation); no phantom rooms reach the Portal | P3 | Negative | Manual | Not Tested
SYN-023 | Deploy | Deployment progress tracking parity | 1. RM: deploy a room; watch WebSocket deployment progress (tasks/subtasks/percentage) 2. On completion check Portal | Deployment completes (status completed, 100%); Portal reflects new state only AFTER completion — never during partial deploy; failed deploys leave Portal at last-good state | P1 | Regression | Manual | Not Tested

## Non-Functional
Non-Functional — Regression Tests
Performance, reliability, security, responsiveness, theming
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
NFR-001 | Performance | Page load budgets | 1. Measure cold load of Dashboard, Alerts, Asset Register, Rooms, each Vitals view | Dashboard/Hotlist < 10s, Vitals < 10s, Hotlist tables < 30s at production data volumes (3k+ alerts, 25k+ assets); Rooms list must not hit the 30s timeout | P1 | Regression | Manual | Not Tested
NFR-002 | Performance | Large table interactions | 1. On Asset Register (25k rows): sort, search, paginate rapidly | Responses < 3s per interaction; no duplicate requests; UI stays responsive | P2 | Regression | Manual | Not Tested
NFR-003 | Reliability | Error boundaries recover | 1. Force a component error (known broken pages in dev) 2. Click Try again / navigate away | Error boundary isolates the failure; Try again recovers; navigation away fully resets the boundary (currently sticks on admin pages) | P1 | Regression | Playwright | Not Tested
NFR-004 | Reliability | API failure surfaces clearly | 1. Simulate 5xx on a module API (dev tools blocking) | Friendly error with retry; no infinite spinner; other modules unaffected | P2 | Negative | Manual | Not Tested
NFR-005 | Concurrency | Two users acting on the same alert | 1. User A and B open same unclaimed alert 2. Both click Claim near-simultaneously | One wins; the other gets a clear conflict/refresh message; owner field consistent | P2 | Edge | Manual | Not Tested
NFR-006 | Browser | Cross-browser smoke | 1. Run smoke set on Chrome, Edge, Firefox, Safari | Layout and core flows work on all supported browsers | P2 | Regression | Manual | Not Tested
NFR-007 | Responsive | Half-screen and small laptop widths | 1. Resize to 1366x768 and ~50% width | Sidebar collapses/scrolls; tables scroll horizontally; top-bar controls wrap without overlap; chat bubble doesn't cover pagination | P2 | Regression | Playwright | Not Tested
NFR-008 | Theme | Dark mode coverage | 1. Enable dark mode 2. Sweep all modules incl. modals, badges, charts, empty states | No unreadable text or white flashes; charts re-theme; severity colours keep semantic meaning | P2 | Regression | Manual | Not Tested
NFR-009 | i18n/Locale | Date/time formats consistent | 1. Compare timestamps across modules | Consistent format and timezone (note mixed formats observed: 'dd/mm/yyyy hh:mm', ISO-8601 in Insights tables, 'Jun 7, 2026, 05:31 PM' in Ops history) — confirm intended standard | P3 | Edge | Manual | Not Tested
NFR-010 | Security | Sensitive data masked | 1. Inspect asset credentials, API responses in devtools | Passwords/secrets never returned in plaintext to the browser; app client secrets shown once | P1 | Regression | Manual | Not Tested
NFR-011 | Security | XSS via user-supplied fields | 1. Enter <script>/HTML payloads in notes, incident names, saved view names, attribute values | Rendered as text everywhere (lists, detail panes, exports); no script execution | P1 | Negative | Manual | Not Tested
NFR-012 | Security | IDOR on detail routes | 1. As restricted user, request another group's alert/asset/room detail URL by id | 403/redirect; no data in response body | P1 | Negative | Manual | Not Tested
NFR-013 | Data refresh | Auto-refresh intervals | 1. Observe Last Updated cadence across modules | Data refreshes on the documented interval; refresh does not reset user's scroll/filters | P3 | Regression | Manual | Not Tested
NFR-014 | Export | Export integrity at volume | 1. Export 3k+ alerts and 25k assets | Files complete and parseable; row counts match; runs as background op with progress + completion notification | P2 | Regression | Manual | Not Tested
NFR-015 | BFF | Rate limiting behaviour | 1. Exceed 1000 requests/min from one IP 2. Inspect headers and recovery | 429 with retryAfter; X-RateLimit-Limit/Remaining/Reset headers present; /health exempt; limit resets after 60s window. NOTE: limiter is per-instance in-memory — multi-instance prod behaviour differs | P2 | Regression | API | Not Tested
NFR-016 | BFF | Upstream timeout and error surface | 1. Make backend hang >30s (dev block) 2. Inspect BFF response and UI toast | BFF 30s timeout returns 502 with {error, statusCode, correlationId}; UI shows meaningful toast (not infinite spinner — cf. Rooms timeout bug); correlationId traceable in logs | P1 | Negative | API | Not Tested
NFR-017 | BFF | Health endpoints | 1. GET /health (no auth), GET /health/deep | /health returns ok+uptime without auth; /health/deep HEAD-checks backend + platform API (5s timeout) and returns 503 with per-check status when degraded | P2 | Regression | API | Not Tested
NFR-018 | BFF | Request body limits | 1. POST >1MB JSON body to any endpoint | 413 returned cleanly; no BFF crash; error shape consistent | P3 | Negative | API | Not Tested
NFR-019 | Security | Tenant filter injection on insights search (cross-tenant defense) | 1. POST /api/insights/search with a query that omits or fakes another tenant in metadata.tenant filter | BFF injects/enforces term metadata.tenant.keyword=<own tenant> (idempotent); cross-tenant data never returned (defense-in-depth with platform API) | P1 | Negative | API | Not Tested
NFR-020 | Resilience | WebSocket reconnection strategy | 1. Drop the WS connection repeatedly (network toggle) 2. Observe reconnect timing | Reconnects with exponential backoff (v3 spec: 3s doubling to 60s cap, max 20 attempts); UI indicates degraded real-time state; no message loss on resume (or full refetch) | P2 | Edge | Manual | Not Tested

## Known Issues & Edge Cases
Known Issues & Edge Cases — Regression Tests
Live defects found 10/06/2026 + historical edge cases to keep under regression
Test ID | Category | Test Case | Steps | Expected Result | Priority | Type | Automation | Status | Tested By | Date | Notes / Defect
BUG-001 | Open Bug | Asset detail Status tab crash | Repro 10/06/2026 dev: Assets > any asset > Status tab | 'Something went wrong — e is not iterable' error boundary. Expected: live status renders. Retest after fix; add Playwright guard | P1 | Regression | Playwright | Not Tested
BUG-002 | Open Bug | Integration routes render wrong module | Repro: deep-link /integrations/appspace or /integrations/microsoft-teams-room (and sidebar nav for Appspace) | QSC Q-Sys module renders instead of the selected integration. Expected: each route renders its own module incl. on refresh | P1 | Regression | Playwright | Not Tested
BUG-003 | Open Bug | Rooms list/detail timeout | Repro: Rooms page under All Sites (and with search filter) | 'Failed to load rooms — timeout of 30000ms exceeded'; room detail spinner never resolves. Expected: loads at production scale | P1 | Regression | Playwright | Not Tested
BUG-004 | Open Bug | Admin Audit Logs crash + sticky error boundary | Repro: Administration > Audit Logs | Crash: '<Select.Item /> must have a value prop that is not an empty string'; boundary persists when clicking other admin items until Try again. Expected: page loads; boundary resets on route change | P1 | Regression | Playwright | Not Tested
BUG-005 | Open Bug | ServiceNow incident template not evaluated | Repro: Incident detail INC3399369 (Room Outage) | Description shows raw JSONata: '"Room " & room.name & ...'; Room Details panel stuck 'Loading room details...'. Expected: evaluated description + room panel loads | P2 | Regression | Manual | Not Tested
BUG-006 | Open Bug | Dashboard KPI cards stuck as skeletons | Repro: intermittent on Dashboard load (2 of 5 cards) | Cards never resolve on some loads. Expected: all cards resolve or show explicit error | P2 | Regression | Playwright | Not Tested
BUG-007 | Watch | Alert detail room link no-op | Repro: Alert detail > Room Details > room name button | Click does not navigate (likely blocked by Rooms backend issue). Expected: opens room support view | P2 | Regression | Playwright | Not Tested
BUG-008 | Historical | Alert history user-group filter | From v3 plan notes: 'user group filtering not working' on Alert History filters | Verify v4 alert history filters by user group correctly | P2 | Regression | Manual | Not Tested
BUG-009 | Historical | Alert lifecycle ordering anomalies | From v3 plan: events must make logical sense | No resolve-twice, no resurface-without-resolve in any alert history; add automated lifecycle-order assertion | P2 | Edge | Playwright | Not Tested
BUG-010 | Historical | Suppression definitions honoured | From v3 plan: suppressed alerts correlate to definitions (In Maintenance, Is Portable) | Suppression reasons traceable to room/asset flags; un-flagging resumes alerting | P2 | Regression | Manual | Not Tested
BUG-011 | Historical | Duplicate room attributes | Dev data has duplicate 'Camera Input' attributes | Decide/enforce uniqueness policy; ensure Information views and conditions behave deterministically with duplicates | P3 | Edge | Manual | Not Tested
BUG-012 | Historical | Lamp-hours threshold alerts | Legacy edge case: projector lamp hour current value must increase over time in alert detail | Current Value updates as device lamp hours increase; threshold alert resolves when lamp replaced/counter reset | P3 | Regression | Manual | Not Tested
BUG-013 | Open Bug | Asset Register search does not filter | Repro 10/06/2026 dev: Assets > Asset Register, type a room name in 'Search assets...', press Enter | Table remains at full 25,408 rows; no re-query fires. Expected: server-side filtered results. Blocks room-level asset reconciliation via UI | P1 | Regression | Playwright | Not Tested
BUG-014 | Watch | Possible RM->Portal asset drift (Display 1) | Portal shows suppressed alerts for 'Display 1' in room Chatswood-L17B-HR05-S5, but RM Devices (Control) lists only Decoder 3, Display 4, PDU 3 | Verify whether 'Display 1' exists under RM Monitoring group; if not, Portal holds a stale asset for a device removed from RM — run the device reconciliation tests | P1 | Regression | Manual | Not Tested
BUG-015 | Watch | Axis AI insights stored in-memory (BFF scaffold) | Code: innomesh-ui-portal-bff src/lib/axis-ai-store.ts — per-user Map, max 50 insights/200 log entries, TODO real persistence | Saved insights/query logs are LOST on BFF restart. Decide persistence approach before GA; retest after fix | P2 | Regression | API | Not Tested
BUG-016 | Watch | BFF rate limiter is per-instance only | Code: rate-limiter middleware uses in-memory Map per IP | In multi-instance prod the effective limit multiplies by instance count; confirm acceptable or move to shared store | P3 | Edge | Manual | Not Tested
BUG-017 | Historical | v3 deep links must not 404 in v4 | Customers have bookmarked v3 URLs (/Hotlist?room=&asset=&tab=, /Rooms/{id}/{name}, /Information/Detail-View/{room}) | Decide redirect mapping or document breaking change; test the common bookmarked patterns against v4 router | P2 | Edge | Playwright | Not Tested